## Settings
Team Member | Role | Department | Primary Focus | Sprint Capacity (hrs/wk) | Owns | Does NOT Do
abhishek | CEO / All-Rounder | Product + Engineering | Product decisions, priorities, beta, legal, partnerships + jumps into coding/infra/reviews when needed | 50 | Executive Dashboard, Launch Countdown, Weekly Review, critical eng reviews | Nothing off-limits — but default eng work goes to sunish/aaradhya
sunish | Engineer — Infra, Trading, AI | Engineering | GCP/Cloud Run, MetaAPI, bots, copy trading, AI Coach, sync pipeline, load tests, Sentry, backups | 45 | Deployment Tracker, Trading/Coach features, load/UAT eng | Marketing content / social
aaradhya | Engineer — Frontend, Web, Product UI | Engineering | Frontend/UI, landing LCP, /status, onboarding UX, dashboard polish, web SEO implementation, PostHog wiring, marketing-page code | 45 | Feature Matrix (web), Website eng, Testing (UI), SEO code fixes | Social posting / blog writing
abhishek kushwaha | Marketing — Growth & Acquisition | Marketing | User acquisition, partnerships, beta invites, community growth, campaigns, prospect lists, competitor intel | 45 | Marketing Plan (growth), KPI acquisition, community | Coding / deploys
ishit | Marketing — Content & Brand | Marketing | Blogs, guides, social, website copy, brand voice, email copy, FAQs, Shorts/creatives | 45 | SEO Tracker (content), Marketing Plan (content), Website Checklist (copy) | Coding / deploys
Quick rule | Detail
Coding | sunish + aaradhya (+ abhishek when needed)
Marketing | abhishek kushwaha (growth) + ishit (content)
Product lead | abhishek (all-rounder)
Phase | Planning ¦ Development ¦ Testing ¦ Deployment ¦ Marketing ¦ Ops
Priority | Critical ¦ High ¦ Medium ¦ Low
Status | Not Started ¦ In Progress ¦ Review ¦ Blocked ¦ Completed ¦ Deferred
Task Type | Epic ¦ Feature ¦ Bug ¦ Chore ¦ UAT ¦ Ops ¦ Content ¦ SEO ¦ Campaign ¦ Support

## Executive Dashboard
PROFYTRON — EXECUTIVE DASHBOARD
Updated 2026-07-30 · accuracy-pass · Coding=sunish+aaradhya · Marketing=kushwaha+ishit · PUBLIC=Get Bots only
Metric | Value |  | Team Member | Role | Open Tasks | Est Hours
Total Tasks | 104 |  | abhishek | CEO / All-Rounder | 17 | 118
Completed | 13 |  | sunish | Eng — Infra/Trading/AI | 29 | 175
In Progress | 9 |  | aaradhya | Eng — Frontend/Web | 21 | 119
Blocked | 0 |  | abhishek kushwaha | Marketing — Growth | 10 | 121
Not Started | 76 |  | ishit | Marketing — Content | 15 | 113
Deferred | 6
Remaining (excl deferred) | 85
Est hours active | 646
WHO DOES WHAT (CORRECTED)
abhishek — All-Rounder (Product lead + can code/review/ops anytime)
Priorities, beta, legal, partnerships, GSC/allowlist, PR reviews, incident response, fills gaps
sunish — Engineering (Infra, Trading, AI, Backend)
GCP, MetaAPI, bots, coach backend, payments/auth UAT, security, load tests, Sentry, DB backups
aaradhya — Engineering (Frontend, Web, Product UI)
Landing LCP, /status, onboarding, dashboard UI, SEO code, PostHog, billing UI, Safari auth, marketing page impl
abhishek kushwaha — Marketing Growth (NO coding)
Acquisition, partnerships, invites, community, campaigns, prospect lists, competitor intel
ishit — Marketing Content (NO coding)
Blogs, guides, social, website copy, brand, email copy, FAQs, Shorts
LAUNCH READINESS
Area | Status | Next Action | Owner
Website code / LCP | Partial | Ship LCP <4s; /status DONE | aaradhya
Website copy | Not Started | Hero + pricing + blogs — no publish evidence | ishit
Auth live OTP | Completed | OTP UAT evidence 2026-07-28 | sunish
Payments live | Blocked | Execute live Razorpay checkout + webhook UAT | sunish
MetaAPI live | Blocked | Get Bots live UAT (MT5 connect + bot activate) | sunish
AI Coach | Partial | Keys UAT + UI polish + content | sunish / aaradhya / ishit
Infrastructure | Completed | GCP API healthy; restore drill + alert channel optional | sunish (+ abhishek)
Acquisition | Not Started | 100 prospects + Discord — no evidence | abhishek kushwaha
Closed beta | Not Started | Allowlist + invites | abhishek
TOP 3 BLOCKERS
1. Live Payments UAT (checkout + webhook) — sunish
2. Get Bots live UAT (MetaAPI connect + bot activate) — sunish
3. Marketing engine (prospects + blogs + Discord) + trial prod deploy — kushwaha/ishit/sunish
RULE: Coding = sunish + aaradhya (+ abhishek as all-rounder). Marketing-only = abhishek kushwaha + ishit.

## Master Tracker
Task ID | Task Name | Owner | Phase | Department | Sprint | Priority | Status | Risk Level | Task Type | Estimated Hours | Actual Hours | Notes / Evidence
PT-E01 | Track D — Launch Readiness (live ops proofs) | abhishek | Ops | Product | Sprint 1 | Critical | In Progress | Critical | Epic | 30 | 22 | Track D: API healthy, OTP UAT pass, Sentry/uptime/DNS done. Open: Payments UAT, MetaAPI/Get-Bots UAT, beta, marketing. 2026-07-30.
PT-E02 | Closed Beta 20–50 users | abhishek | Ops | Product | Sprint 2 | Critical | Not Started | High | Epic | 25 | 0 | CLOSED_BETA_PLAYBOOK.md
PT-E03 | Scale to 100 users | abhishek | Ops | Product | Sprint 4 | High | Not Started | High | Epic | 20 | 0
PT-E04 | Marketing engine for acquisition | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Epic | 60 | 0 | Growth lead; ishit content
PT-D01 | Pick primary production backend (GCP Cloud Run) | sunish | Deployment | Engineering | Sprint 1 | Critical | Completed | Critical | Ops | 6 | 6 | Primary backend = GCP Cloud Run. Confirmed PRODUCTION_STATUS.md + live. 2026-07-30.
PT-D02 | Deploy API to GCP Cloud Run min-instances=1 | sunish | Deployment | Engineering | Sprint 1 | Critical | Completed | Critical | Ops | 12 | 12 | API Cloud Run min-instances=1. /live /ready /health=200 gitSha 1044ce5. Probed 2026-07-30.
PT-D03 | Deploy Web + ship /status to prod | aaradhya | Deployment | Engineering | Sprint 1 | Critical | Completed | High | Ops | 8 | 8 | /status live 200 on www.profytron.com (verified 2026-08-02).
PT-D04 | Verify /live /ready /health = 200 on prod API | sunish | Deployment | Engineering | Sprint 1 | Critical | Completed | Critical | UAT | 4 | 4 | Was Blocked 2026-07-19. Green since ~2026-07-23. Re-probed 200s on 2026-07-30.
PT-D05 | Wire Sentry DSN API + Web | sunish | Deployment | Engineering | Sprint 1 | High | Completed | High | Ops | 3 | 3 | API Sentry wired Day 5. Web NEXT_PUBLIC_SENTRY_DSN via cloudbuild.
PT-D06 | Enable Cloud SQL backups + remove duplicate instance | sunish | Deployment | Engineering | Sprint 1 | Critical | Completed | Critical | Ops | 6 | 6 | Prod backups ON (retain 7). Unused instance profytron STOPPED/NEVER — not deleted yet. Acceptable as Completed with this note.
PT-D07 | DB backup restore drill + record date | sunish | Ops | Engineering | Sprint 2 | High | Not Started | High | Ops | 6 | 0 | Restore drill + dated evidence still outstanding.
PT-D08 | Uptime alerts on /health | sunish | Ops | Engineering | Sprint 1 | High | In Progress | High | Ops | 4 | 4 | Uptime CHECK exists (api-health every 60s, 2026-07-23). Alert/notification channel NOT done — tracked as PT-D11. Downgraded from Completed for accuracy 2026-07-30.
PT-D09 | Write deploy RUNBOOK (single source of truth) | abhishek | Ops | Product | Sprint 1 | Medium | In Progress | Medium | Chore | 3 | 1 | Runbooks exist under docs/tracks/D-launch-readiness/runbooks/*. Consolidation still open.
PT-D10 | Re-run k6 load test 100 VUs | sunish | Testing | Engineering | Sprint 2 | Critical | Not Started | Critical | UAT | 8 | 2 | API healthy now. Formal k6 100 VU re-run still outstanding.
PT-A01 | Live email OTP UAT (Resend inbox proof) | sunish | Testing | Engineering | Sprint 1 | Critical | Completed | Critical | UAT | 8 | 8 | Formal live OTP UAT PASS 2026-07-28. Evidence: D7_OTP_UAT_20260728.md
PT-A02 | SPF/DKIM/DMARC for sending domain | sunish | Ops | Engineering | Sprint 1 | Critical | Completed | High | Ops | 4 | 4 | Resend domain verified. DKIM + SPF(send) + DMARC. Day 6.
PT-A03 | EXPOSE_DEV_OTP OFF in production | sunish | Ops | Engineering | Sprint 1 | Critical | Completed | Critical | Ops | 1 | 1 | EXPOSE_DEV_OTP absent in SM/Cloud Run. Confirmed Day 5 + Day 7.
PT-A04 | Safari/iOS login + refresh cookie fix/QA | aaradhya | Testing | Engineering | Sprint 1 | High | Review | High | Bug | 6 | 5 | Secure client cookies + pf_session_hint Safari race fix in useAuthStore. Code verification doc done. Device Safari/iOS video still outstanding for Completed.
PT-A05 | Google + GitHub OAuth smoke test | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 4 | 0 | Google+GitHub OAuth smoke still outstanding.
PT-A06 | 2FA enroll + login smoke test | sunish | Testing | Engineering | Sprint 2 | Medium | Not Started | Medium | UAT | 3 | 0 | 2FA smoke still outstanding.
PT-A07 | Forgot/reset password end-to-end | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 3 | 0 | Forgot/reset password full E2E not signed off.
PT-A08 | Set BETA_ALLOWLIST_EMAILS in prod | abhishek | Ops | Product | Sprint 2 | Critical | Not Started | High | Ops | 2 | 0 | BETA_ALLOWLIST_EMAILS not applied.
PT-A09 | Auth journey UI polish (verify-email screens) | aaradhya | Development | Engineering | Sprint 1 | Medium | Completed | Low | Feature | 4 | 4 | Verify-email journey UI polish shipped.
PT-P01 | Live Stripe/Razorpay checkout UAT | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 10 | 0 | Day 8 = read-only audit only. No live checkout UAT yet.
PT-P02 | Webhook → entitlement proof | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 6 | 0 | Live webhook entitlement proof outstanding.
PT-P03 | Billing UI polish + plan cards | aaradhya | Development | Engineering | Sprint 1 | High | Completed | Medium | Feature | 5 | 5 | Billing plan cards + full features + trial banner/StartTrial UI ship-ready on prod.
PT-P04 | Wallet smoke test | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 6 | 0
PT-P05 | Pricing messaging strategy / A/B ideas | abhishek kushwaha | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Campaign | 4 | 0
PT-T01 | Live MetaAPI MT5 connect UAT | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 12 | 0 | Live MetaAPI MT5 connect UAT outstanding (Get Bots path).
PT-T02 | Account sync → dashboard balance proof | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 8 | 0 | Account sync -> dashboard balance proof outstanding.
PT-T03 | Copy-subscribe UAT (FOLDED -> use PT-T04 bots) | sunish | Testing | Engineering | Sprint 2 | Low | Deferred | Low | UAT | 10 | 0 | INTERNAL: NOT separate product. Folded into PT-T04 (Get Bots / master_only bridge).
PT-T04 | Bot marketplace -> active bot UAT (PRIMARY trading path) | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 8 | 0 | PRIMARY trading UAT: marketplace -> active bot on user MT5 (master_only bridge).
PT-T05 | Paper trading path for new users | sunish | Development | Engineering | Sprint 2 | High | Not Started | Medium | Feature | 8 | 0
PT-T06 | WebSocket gateway stability under load | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 6 | 0
PT-T07 | Get Bots / connected-accounts UI polish | aaradhya | Development | Engineering | Sprint 2 | High | Completed | Medium | Feature | 8 | 8 | Get Bots + connected-accounts empty/error states shipped in apps/web.
PT-T08 | Recruit 5 traders for MetaAPI beta testing | abhishek kushwaha | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Campaign | 8 | 0
PT-C01 | AI Coach live stream with prod keys | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 6 | 0
PT-C02 | Coach Insights migration + admin confirm | sunish | Deployment | Engineering | Sprint 1 | High | Not Started | Medium | Ops | 4 | 0 | abhishek reviews admin
PT-C03 | Alpha Coach UI polish + empty states | aaradhya | Development | Engineering | Sprint 2 | Medium | Completed | Low | Feature | 5 | 5 | Alpha Coach bootstrap skeleton + empty/error polish shipped.
PT-C04 | AI Coach explainer content + FAQ copy | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 8 | 0
PT-W01 | Landing LCP < 4s (lazy-load 3D/motion) | aaradhya | Development | Engineering | Sprint 1 | Critical | Completed | High | Feature | 16 | 16 | LCP path shipped: LandingHeavyShell defer + idle FX; mobile no ambient/WebGL. Prod web-00074-nkc. 3.93s median mobile Lighthouse (3.42/3.93/3.97) PASS <4s. Evidence: docs/aaradhya-45-day-complete-plan/evidence/day-13/PT-W01-lighthouse-median.md
PT-W02 | Mobile responsive QA all public pages | aaradhya | Testing | Engineering | Sprint 1 | High | Completed | Medium | Chore | 10 | 10 | Mobile public/nav overflow + quieter polling (accounts 60s, markets/history no background refetch).
PT-W03 | Implement approved homepage hero/CTA in code | aaradhya | Development | Engineering | Sprint 1 | Critical | Partial | Medium | Feature | 4 | 2 | Default Start 7-Day Free Trial CTAs live. Full ishit-approved hero copy/art still pending.
PT-W04 | Rewrite homepage hero + CTA copy | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 6 | 0
PT-W05 | Pricing page copy | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 5 | 0
PT-W06 | Onboarding + risk page UX/code polish | aaradhya | Development | Engineering | Sprint 2 | High | Completed | Medium | Feature | 8 | 8 | Onboarding welcome steps + risk polish + ONBOARDING_COMPLETED / analytics wire.
PT-W07 | Onboarding copy | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 4 | 0
PT-W08 | OG/PWA image assets implementation | aaradhya | Development | Engineering | Sprint 2 | Low | Review | Low | Chore | 3 | 3 | OG 1200x630 dims + apple icon/PWA icons in code. Custom ishit OG art optional residual.
PT-S01 | Verify sitemap/robots on prod + fix if broken | aaradhya | Marketing | Engineering | Sprint 1 | High | Completed | Medium | SEO | 3 | 3 | robots.txt + sitemap.xml HTTP 200 on www.profytron.com.
PT-S02 | Submit sitemap to Google Search Console | abhishek | Marketing | Product | Sprint 1 | High | Not Started | Medium | SEO | 2 | 0 | GSC sitemap submit — no evidence.
PT-S03 | Title/meta/OG audit + code fixes on key pages | aaradhya | Marketing | Engineering | Sprint 1 | High | Completed | Medium | SEO | 6 | 6 | pageSeo/meta expanded across key public pages.
PT-S04 | JSON-LD Rich Results validation + fixes | aaradhya | Marketing | Engineering | Sprint 1 | Medium | Completed | Low | SEO | 3 | 3 | JSON-LD + FAQ schema wired (home/help/pricing).
PT-S05 | Write + publish: What is Copy Trading | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 10 | 0
PT-S06 | Write + publish: MT5 Automation with Profytron | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 10 | 0
PT-S07 | Write + publish: AI Trading Coach explained | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 10 | 0
PT-S08 | Write guide: Connect MT5 step-by-step | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0
PT-S09 | Write guide: Risk management for copy traders | ishit | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Content | 8 | 0
PT-S10 | Brokers hub content + page SEO improvements | aaradhya | Marketing | Engineering | Sprint 2 | High | Partial | Medium | SEO | 8 | 4 | Brokers hub SEO intro + setup steps shipped. Long-form broker content = ishit.
PT-S11 | Internal linking implementation | aaradhya | Marketing | Engineering | Sprint 2 | Medium | Completed | Low | SEO | 4 | 4 | Internal linking across public footer/nav/related pages.
PT-S12 | Maintain SEO Tracker weekly | ishit | Marketing | Marketing | Sprint 1 | High | In Progress | Medium | SEO | 3 | 1 | Keywords + content status
PT-S13 | Competitor keyword & landing teardown | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Campaign | 8 | 0 | Feeds ishit/aaradhya
PT-M01 | Wire PostHog in production (code) | aaradhya | Ops | Engineering | Sprint 1 | Critical | Review | High | Ops | 5 | 5 | PostHog provider consent-gated + web vitals path. Confirm prod NEXT_PUBLIC_POSTHOG_KEY with ops.
PT-M02 | Define activation funnel with abhishek | abhishek | Planning | Product | Sprint 1 | High | Not Started | Medium | Chore | 3 | 0 | aaradhya implements events
PT-M03 | Beta invite + welcome email copy (3 emails) | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0 | sunish/aaradhya wire Resend if needed
PT-M04 | Set up Discord/Telegram beta community | abhishek kushwaha | Ops | Marketing | Sprint 2 | Critical | Not Started | High | Campaign | 6 | 0
PT-M05 | Social calendar 12 posts (LinkedIn/X) | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 10 | 0
PT-M06 | Record 3 YouTube Shorts / Reels | ishit | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Content | 10 | 0
PT-M07 | Press kit /press content refresh | ishit | Marketing | Marketing | Sprint 3 | Low | Not Started | Low | Content | 5 | 0
PT-M08 | Community page CTAs + invite links | aaradhya | Development | Engineering | Sprint 2 | Medium | Completed | Low | Feature | 3 | 3 | Community Discord primary CTA live (not Coming Soon).
PT-M09 | Partnership outreach: 10 brokers/creators | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Campaign | 12 | 0 | abhishek joins key calls
PT-M10 | Beta waitlist / invite list of 100 prospects | abhishek kushwaha | Marketing | Marketing | Sprint 1 | Critical | Not Started | High | Campaign | 10 | 0
PT-M11 | Help center top 15 FAQs rewrite | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0
PT-M12 | Weekly growth report | abhishek kushwaha | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Campaign | 3 | 0
PT-M13 | Referral messaging for beta users | abhishek kushwaha | Marketing | Marketing | Sprint 3 | Medium | Not Started | Low | Campaign | 4 | 0
PT-M14 | India GTM angle (Razorpay, local posts) | abhishek kushwaha | Marketing | Marketing | Sprint 2 | Medium | Not Started | Medium | Campaign | 6 | 0 | ishit assets
PT-M15 | Contact form → support reply process | abhishek | Ops | Product | Sprint 1 | High | Not Started | Medium | Support | 2 | 0 | All-rounder owns ops process
PT-L01 | Legal sign-off Privacy + Terms + Risk | abhishek | Ops | Product | Sprint 2 | High | Not Started | High | Chore | 4 | 0
PT-L02 | Cookie banner / policy UX check | aaradhya | Testing | Engineering | Sprint 2 | Medium | Completed | Medium | Feature | 3 | 3 | CookieConsentBanner + consent gate for analytics shipped.
PT-L03 | Support SLA + on-call rotation | abhishek | Ops | Product | Sprint 2 | High | Not Started | High | Ops | 3 | 0
PT-L04 | Chatbot keys + FAQ content pack wiring | aaradhya | Ops | Engineering | Sprint 2 | Medium | Completed | Low | Ops | 4 | 4 | Help FAQ pack + chatbot open wiring shipped (content can grow with ishit).
PT-X01 | Security checklist D2 + secret rotation | sunish | Ops | Engineering | Sprint 2 | High | In Progress | High | Ops | 8 | 4 | D2 first pass + secret rotation PLAN documented. Rotations NOT executed.
PT-X02 | Security Playwright suite + evidence | sunish | Testing | Engineering | Sprint 2 | High | Not Started | Medium | UAT | 6 | 0
PT-X03 | Rotate AES_MASTER_KEY + JWT for prod | sunish | Ops | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 3 | 0 | Rotation plan ready; no secrets rotated as of 2026-07-30.
PT-X04 | Rate-limit smoke test register/login | sunish | Testing | Engineering | Sprint 1 | Medium | Not Started | Medium | UAT | 2 | 0
PT-K01 | Lock KPI targets for beta | abhishek | Planning | Product | Sprint 1 | High | Not Started | Medium | Chore | 3 | 0
PT-K02 | Weekly Coach Insights review | abhishek | Ops | Product | Sprint 3 | Medium | Not Started | Low | Ops | 2 | 0
PT-K03 | Instrument time-to-first-broker in PostHog | aaradhya | Marketing | Engineering | Sprint 2 | High | Completed | Medium | Feature | 3 | 3 | time_to_first_broker PostHog event instrumented on broker connect.
PT-R01 | Daily standup logged every weekday | abhishek | Ops | Product | Sprint 1 | Medium | Not Started | Low | Chore | 5 | 0
PT-R02 | Friday Weekly Review | abhishek | Ops | Product | Sprint 1 | Medium | Not Started | Low | Chore | 2 | 0
PT-R03 | Keep Executive Dashboard updated | abhishek | Ops | Product | Sprint 1 | High | In Progress | Low | Chore | 2 | 1 | Executive Dashboard synced by writer 2026-07-30.
PT-E05 | Code review critical PRs (auth/payments/MetaAPI) | abhishek | Ops | Engineering | Sprint 1 | High | Not Started | Medium | Chore | 6 | 0 | All-rounder eng oversight
PT-E06 | Pair on production incident response | abhishek | Ops | Engineering | Sprint 1 | High | Not Started | High | Ops | 4 | 0 | With sunish/aaradhya as needed
PT-Z01 | Track B Strategy Builder build | sunish | Planning | Engineering | Backlog | Low | Deferred | Low | Epic | 80 | 0 | aaradhya UI when opened
PT-Z02 | Track C Marketplace growth features | abhishek | Planning | Product | Backlog | Low | Deferred | Low | Epic | 40 | 0
PT-Z03 | External Statuspage | sunish | Ops | Engineering | Backlog | Low | Deferred | Low | Ops | 6 | 0
PT-Z04 | Open GA registration (no allowlist) | abhishek | Ops | Product | Backlog | Medium | Deferred | High | Ops | 4 | 0
PT-Z05 | Affiliate soft launch | abhishek kushwaha | Marketing | Marketing | Backlog | Low | Deferred | Low | Campaign | 10 | 0
PT-P06 | 7-Day platform trial — implement + RC validate | sunish | Development | Engineering | Sprint 1 | Critical | Completed | High | Feature | 16 | 16 | Schema+API+UI+emails+cron. RC 2026-07-29. NOT on prod (gitSha 1044ce5).
PT-P07 | Trial start TOCTOU race fix (FOR UPDATE) | sunish | Development | Engineering | Sprint 1 | Critical | Completed | High | Bug | 4 | 4 | Fixed+verified 2026-07-30. docs/audits/trial-race-condition-fix-2026-07-30.md
PT-P08 | Deploy trial feature to production | sunish | Deployment | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 4 | 0 | Needs migrate deploy + API/web ship. Prod still pre-trial.
PT-P09 | Manual browser QA: trial start -> banner -> upgrade | aaradhya | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 2 | 0 | Trial UAT checklist ready under evidence/day-13/PT-P09-trial-qa-checklist.md — needs human browser UAT on Stripe.
PT-T09 | INTERNAL: bot-only public surface (no separate copy product) | abhishek | Ops | Product | Sprint 1 | High | Completed | Medium | Chore | 1 | 1 | Customers see Get Bots only. Eng copy = master_only MetaAPI bridge. Locked 2026-07-30.
PT-X05 | Razorpay webhook Redis outage soft-fail | sunish | Development | Engineering | Sprint 1 | High | Not Started | High | Bug | 3 | 0 | Pre-existing redis.set lock has no try/catch. Found in trial gate.
PT-D11 | Uptime check -> alert notification channel | sunish | Ops | Engineering | Sprint 1 | Medium | Not Started | Medium | Ops | 2 | 0 | api-health check exists; paging policy optional.

## Feature Matrix
Feature ID | Feature Name | Eng Owner | Marketing Owner | Code Status | Live Proof | Content Status | Overall | Notes
F-01 | Marketing website | aaradhya | ishit | Completed | Partial | Partial | Partial | Site live; LCP/copy still partial.
F-02 | SEO system | aaradhya | ishit | Completed | Partial | Not Started | Partial | robots+sitemap 200; content SEO not published.
F-03 | Blog + Guides | aaradhya | ishit | Completed | Partial | Not Started | Partial
F-04 | Brokers hub | aaradhya | ishit | Completed | Partial | Partial | Partial
F-05 | Auth + OTP | sunish | — | Completed | Completed | N/A | Partial | OTP live UAT PASS 2026-07-28. OAuth/2FA/Safari still open.
F-06 | OAuth | sunish | — | Completed | Not Started | N/A | Partial
F-07 | 2FA + magic link | sunish | — | Completed | Not Started | N/A | Partial
F-08 | Closed beta allowlist | abhishek | abhishek kushwaha | Completed | Not Started | N/A | Not Started | Allowlist code exists; prod beta list not set.
F-09 | Billing | sunish | abhishek kushwaha | Completed | Partial | Partial | Partial | Plans live. Live checkout UAT NOT done. Trial local only.
F-10 | Wallet | sunish | — | Completed | Not Started | N/A | Partial
F-11 | Dashboard | aaradhya | ishit | Completed | Partial | Partial | Partial
F-12 | MT5 / Connected accounts | sunish | abhishek kushwaha | Completed | Not Started | Not Started | Partial | MT5 connect required for Get Bots. Live UAT open.
F-13 | Copy bridge (INTERNAL — not public product) | sunish | ishit | Completed | Deferred | N/A | Deferred | INTERNAL: public = Get Bots. Eng = master_only MetaAPI bridge behind F-14.
F-14 | Bots marketplace | sunish | abhishek kushwaha | Completed | Not Started | Partial | Partial | PRIMARY product: Get Bots / marketplace. Live UAT = PT-T04.
F-15 | AI Coach | sunish | ishit | Completed | Partial | Not Started | Partial | UI = aaradhya
F-16 | Coach Insights | sunish | abhishek | Completed | Not Started | N/A | Not Started
F-17 | Notifications | sunish | ishit | Completed | Not Started | Partial | Partial
F-18 | Support + chatbot | aaradhya | ishit | Completed | Not Started | Partial | Partial
F-19 | Help / Docs | aaradhya | ishit | Completed | Partial | Partial | Partial
F-20 | Legal pages | aaradhya | abhishek | Completed | Partial | Completed | Partial
F-21 | Status page | aaradhya | — | Completed | Completed | N/A | Completed | www.profytron.com/status = 200 (2026-07-30).
F-22 | PostHog | aaradhya | abhishek | Completed | Not Started | N/A | Not Started
F-23 | Sentry | sunish | — | Completed | Completed | N/A | Completed | API Sentry fully configured Day 5.
F-24 | CI/CD + GCP | sunish | — | Completed | Completed | N/A | Partial | GCP Cloud Run healthy; uptime check on.
F-25 | Strategy Builder | sunish | — | Partial | Deferred | N/A | Deferred
F-26 | Affiliate | aaradhya | abhishek kushwaha | Completed | Deferred | Not Started | Deferred
F-27 | 7-Day Platform Trial | sunish | abhishek kushwaha | Completed | Not Started | Partial | Partial | Local code+RC+race fix done 2026-07-29/30. NOT deployed (prod gitSha 1044ce5).

## SEO Tracker
Keyword | Volume | Difficulty | Landing Page | Rank | Target | Status | Content Owner | Eng SEO Owner | Priority | Notes
bot trading platform | High | High | /pricing | NR | Top 10 | Not Started | ishit | aaradhya | Critical
best copy trading software | High | High | /pricing | NR | Top 10 | Not Started | ishit | aaradhya | Critical
MT5 copy trading | High | Medium | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Critical
MetaTrader 5 automation | Medium | Medium | /blog | NR | Top 10 | Not Started | ishit | aaradhya | High
AI trading coach | Medium | Low | /blog | NR | Top 5 | Not Started | ishit | aaradhya | High
how to connect MT5 to copy trading | Medium | Low | /guides | NR | Top 3 | Not Started | ishit | aaradhya | Critical
what is copy trading | High | Medium | /blog | NR | Top 5 | Not Started | ishit | aaradhya | Critical
Profytron | Brand | Low | / | NR | 1 | Not Started | ishit | aaradhya | Critical
Profytron pricing | Brand | Low | /pricing | NR | 1 | Not Started | ishit | aaradhya | High
social trading platform India | Medium | Medium | / | NR | Top 10 | Not Started | ishit | aaradhya | High | From growth
best MT5 brokers for copy trading | Medium | Medium | /brokers | NR | Top 10 | Not Started | ishit | aaradhya | High
automated forex trading bots | High | High | /marketplace | NR | Top 20 | Not Started | ishit | aaradhya | High
paper trading MT5 | Medium | Low | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Medium
risk management copy trading | Medium | Low | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Medium
trading bot marketplace | Medium | Medium | /marketplace | NR | Top 15 | Not Started | ishit | aaradhya | Medium
Exness copy trading | Medium | Medium | /brokers | NR | Top 10 | Not Started | ishit | aaradhya | Medium | Competitor input
Razorpay trading subscription | Low | Low | /pricing | NR | Top 5 | Not Started | ishit | aaradhya | Medium | India GTM
forex signal copy trading | Medium | Medium | /copy-trading | NR | Top 10 | Not Started | ishit | aaradhya | High
AI forex assistant | Low | Low | /blog | NR | Top 5 | Not Started | ishit | aaradhya | Medium
Profytron login | Brand | Low | /login | NR | 1 | Not Started | ishit | aaradhya | High

## Deployment Tracker
Environment | Service | Status | Health Check | Owner | Backup Owner | Notes
Production | API (GCP Cloud Run) | Healthy | 200 /live /ready /health | sunish | abhishek | gitSha 1044ce5; min-instances=1; uptime api-health 60s. Probed 2026-07-30.
Production | Web + /status | Healthy | 200 www + /status | aaradhya | abhishek | /status live (was historically 404).
Production | AI Coach service | Partial | Service up; live product UAT open | sunish | abhishek | Cloud Run Ready; PT-C01 still open.
Production | Postgres (Cloud SQL) | Healthy | Backups ON retain-7 | sunish | abhishek | profytron-postgres RUNNABLE. Unused profytron STOPPED. Restore drill pending.
Production | Redis | Healthy | connected via /health | sunish | abhishek | /health redis=connected 2026-07-30.
Legacy | Render free API | Deprecated | Do not use | sunish | abhishek | Primary is GCP. Decommission when confirmed unused.
CI | GitHub Actions | Healthy | PR checks | sunish | aaradhya

## Testing Dashboard
Module | Primary Eng | Secondary | Marketing QA | Eng Status | Overall | Notes
Auth / OTP | sunish | aaradhya | ishit | Completed | Partial | Live OTP UAT PASS 2026-07-28. Safari/OAuth/2FA open.
Payments | sunish | aaradhya | abhishek kushwaha | Partial | Blocked | Day 8 audit only. Live checkout UAT NOT done. Trial local-ready, not prod.
MetaAPI / Broker | sunish | abhishek | abhishek kushwaha | Not Started | Not Started | Required for Get Bots (PT-T01/T02).
Get Bots / Marketplace | sunish | aaradhya | abhishek kushwaha | Not Started | Not Started | PRIMARY trading UAT (PT-T04). No separate Copy Trading track.
AI Coach | sunish | aaradhya | ishit | Partial | Partial | PT-C01 live keys UAT open.
Landing / Web | aaradhya | abhishek | ishit | Partial | Partial | /status live; LCP not signed off.
SEO implementation | aaradhya | — | ishit | Partial | Partial | robots+sitemap 200; blogs not published.
Load / API health | sunish | abhishek | — | Partial | Partial | API healthy. k6 100 VU formal re-run open.
Security | sunish | abhishek | — | Partial | Partial | Rotation plan ready; rotations not done. EXPOSE_DEV_OTP OFF.
Dashboard UI | aaradhya | sunish | ishit | Partial | Partial | Get Bots + connected accounts; bot-labels.ts
7-Day Trial (local) | sunish | aaradhya | abhishek | Completed | Review | RC+fixes+race fix local 2026-07-29/30. Awaiting prod deploy.

## KPI Dashboard
KPI | Current | Target | Owner | Cadence | Notes
Task completion (excl deferred) | see Exec Dashboard | 100% | abhishek | Daily | Recounted from Master Tracker 2026-07-30
API uptime 7d | Healthy now | 99.5% | sunish | Daily | /health 200 since ~2026-07-23; uptime CHECK on. Alert policy still open (PT-D11).
Landing LCP mobile | 3.93s median | <4s | aaradhya | Weekly | 3.93s median mobile Lighthouse (3.42/3.93/3.97) PASS <4s; prod web-00074-nkc; 2026-08-02; docs/.../PT-W01-lighthouse-median.md
OTP deliverability | Pass | Pass | sunish | Once | Day 6 delivered + Day 7 formal UAT PASS
MetaAPI connect success | Unproven | >95% | sunish | Weekly | Live UAT still open
Payment checkout success | Unproven | >95% | sunish | Weekly | Live UAT still open (Day 8 audit only)
Beta prospect list | 0 (no evidence) | 100 | abhishek kushwaha | Weekly | Do not invent progress
Beta invites sent | 0 | 50 | abhishek | Weekly
Activated users (broker) | 0 | 20 | abhishek kushwaha | Weekly
7-day activation rate | — | >30% | aaradhya | Weekly | PostHog code consent-gated + time_to_first_broker live. Confirm prod key for verified funnel metrics.
Blog posts published | 0 (no evidence) | 10 by W6 | ishit | Weekly
Social posts / week | 0 (no evidence) | 3 | ishit | Weekly
Partnerships started | 0 (no evidence) | 10 | abhishek kushwaha | Weekly
Load test 100 VU | Not re-run | Pass | sunish | Once | Earlier Fail was infra-blocked; schedule re-run
Trial feature (local) | Ready | Prod deploy | sunish | Once | RC+race fix done; awaiting PT-P08

## Launch Countdown
Milestone | Target Date | Days Left | Owner | Status | Definition of Done
M0 — Production API stable 24/7 | 2026-07-27 | -3 | sunish (+ abhishek) | Completed | API /health 200 sustained since ~2026-07-23; reconfirmed 2026-07-30
M1 — Live UAT OTP + Payments + MetaAPI | 2026-07-30 | 0 | sunish | In Progress | OTP UAT PASS. Payments + MetaAPI/Get-Bots live UAT still open.
M2 — /status + Sentry + monitoring | 2026-07-30 | 0 | aaradhya + sunish | Completed | /status live + API Sentry + Cloud Monitoring uptime on /health
M3 — LCP <4s + homepage copy live | 2026-08-03 | 4 | aaradhya + ishit | Not Started | Perf + approved copy
M4 — Marketing engine ready | 2026-08-03 | 4 | abhishek kushwaha + ishit | Not Started | 3 blogs, Discord, 100 prospects
M5 — Internal dogfood 5 users | 2026-08-05 | 6 | abhishek | Not Started | 0 SEV1
M6 — Closed beta 20 invites | 2026-08-10 | 11 | abhishek + abhishek kushwaha | Not Started | 20 invites + community
M7 — Expand to 50 | 2026-08-24 | 25 | abhishek kushwaha | Not Started | Activation >30%
M8 — Load test + backup drill | 2026-08-31 | 32 | sunish | Not Started | API no longer blocking; formal k6 + restore drill still open
M9 — 100 users | 2026-09-14 | 46 | abhishek | Not Started | 100 users live
M10 — Open growth push | 2026-09-28 | 60 | abhishek kushwaha | Not Started | Campaigns live

## Daily Standup
Date | Member | Yesterday | Today | Blockers | Priority | Status
2026-07-20 | abhishek | Clarified roles: all-rounder; aaradhya codes; marketing = kushwaha+ishit | Prioritize M0; GSC/allowlist plan; review eng blockers; partner calls | API still the gate | Critical | In Progress
2026-07-20 | sunish | Reviewed GCP + Track D health failures | Cloud Run API stable; backups; OTP/MetaAPI/Payment UAT prep | Prod API downtime history | Critical | In Progress
2026-07-20 | aaradhya | Role updated: Engineer (frontend/web) not marketing-only | Landing LCP plan; /status deploy; auth UI Safari QA; PostHog wiring plan | Need prod web access + design copy from ishit | Critical | In Progress
2026-07-20 | abhishek kushwaha | Growth marketing only (no coding) | 100-prospect list; competitor teardown; partnership outreach | Need positioning one-pager | High | In Progress
2026-07-20 | ishit | Content/brand marketing only (no coding) | Homepage/pricing copy; 3 blog outlines; social calendar | Need screenshots/product facts | High | In Progress
2026-07-30 | abhishek | Sheet sync + trial race fix oversight; Track D evidence review | Apply full sheet sync; prioritize Payments UAT + Get Bots UAT; trial prod deploy decision | Payments + MetaAPI live UAT still open; marketing evidence missing | Critical | In Progress
2026-07-30 | sunish | Trial race FOR UPDATE fix validated locally; API remains healthy on GCP | Prepare Payments live UAT + Get Bots/MetaAPI UAT; plan trial prod deploy (PT-P08) | Live payment keys/UAT window; MetaAPI test account | Critical | In Progress
2026-07-30 | aaradhya | /status live; robots/sitemap 200 | LCP sign-off number; Safari auth QA; billing/trial UI when trial ships | Need approved hero copy from ishit for final hero ship | High | In Progress
2026-07-30 | abhishek kushwaha | No evidenced prospect/community progress in tracker | Build prospect CRM toward 100; Discord/Telegram create; partner outreach | Need positioning one-pager / product facts | High | Not Started
2026-07-30 | ishit | No evidenced blog/social publish in tracker | Homepage/pricing copy v1; blog drafts; social calendar | Need screenshots/product facts from eng | High | Not Started
2026-08-02 | aaradhya | 45-day FE package engineering + deploy earlier this week | Closed all 45 days FE eng; LCP redeploy; Master Tracker + sheet sync | Safari device video; ishit long-form/hero; Stripe trial human UAT | High | Completed

## Weekly Review
Week | Dates | Goals | Eng Focus | Marketing Focus | Owner
W1 | 2026-07-20 → 2026-07-26 | M0 API up DONE; OTP UAT prep DONE; /status DONE; marketing lists/copy — NO evidence | sunish: API/backups/Sentry/uptime DONE · aaradhya: /status DONE, LCP open · abhishek: reviews | kushwaha: prospects+outreach · ishit: copy+blogs outline | abhishek
W2 | 2026-07-27 → 2026-08-02 | OTP UAT PASS. Payments+MetaAPI/Get-Bots UAT OPEN. Blogs/community — NO evidence. | sunish: OTP DONE; Payments/Get-Bots OPEN; trial local-ready · aaradhya: sitemap/robots DONE | Publish content; Discord; partnerships | abhishek
W3 | 2026-08-03 → 2026-08-09 | Dogfood 5; allowlist; legal | Bugfixes from dogfood | Invites prep; FAQs; welcome emails | abhishek
W4 | 2026-08-10 → 2026-08-16 | Beta 20 live | Stability + Get Bots UAT (NOT separate copy-trading track) | Invite campaign + support content | abhishek

## Sprint Board
Sprint | Theme | Dates | sunish | aaradhya | abhishek | abhishek kushwaha | ishit | Status
Sprint 1 | Make it live | 2026-07-20 → 2026-08-02 | API HEALTHY + OTP UAT PASS + Sentry/backups/uptime DONE. Open: Payments UAT, Get Bots/MetaAPI UAT, trial prod deploy. (Public=Get Bots; copy bridge INTERNAL) | /status DONE; robots/sitemap 200. Open: LCP sign-off, Safari auth, PostHog verify, billing UI polish | Priorities, reviews, GSC, allowlist plan, incidents | 100 prospects, partnerships, competitor teardown | Homepage/pricing copy, 3 blogs, social calendar | In Progress
Sprint 2 | Beta ready | 2026-08-03 → 2026-08-16 | Finish UATs, restore drill, trading UAT | Onboarding UX, community links, coach UI, cookies | Dogfood, legal, invites approve, on-call | Discord, invite ops, recruit test traders, growth report | Publish guides, welcome emails, Shorts, FAQs | Not Started
Sprint 3 | Scale 50 | 2026-08-17 → 2026-08-30 | Beta bugfixes, coach insights | Activation instrumentation, UI polish | Coach Insights review, priorities | Scale invites, referral, partnerships | More content + case studies | Not Started
Sprint 4 | 100 users | 2026-08-31 → 2026-09-13 | Load test pass, infra scale | Growth page tweaks | Go/no-go for 100 | Acquisition to 100 | Creative assets | Not Started

## Marketing Plan
Week | Owner | Lane | Action | Status | KPI Impact | Eng Dependency | Accuracy note 2026-07-30 | All marketing rows remain Not Started unless proof exists. Do not invent CRM/blog/social progress.
W1 | abhishek kushwaha | Growth | Build beta prospect list to 100 | Not Started | Invites ready | None
W1 | abhishek kushwaha | Growth | Competitor landing/pricing teardown | Not Started | Messaging | Share brief with ishit/aaradhya
W1 | abhishek kushwaha | Growth | Start 10 partnership outreach threads | Not Started | Pipeline | abhishek joins calls
W1 | ishit | Content | Homepage hero + CTA copy | Not Started | Conversion | aaradhya implements
W1 | ishit | Content | Pricing page messaging | Not Started | Conversion | aaradhya implements
W1 | ishit | Content | Draft 3 blogs (copy trading, MT5, AI coach) | Not Started | Organic | aaradhya helps publish if CMS/code
W1 | ishit | Content | 12-post social calendar | Not Started | Awareness | None
W2 | abhishek kushwaha | Growth | Launch Discord/Telegram | Not Started | Community | aaradhya wires site links
W2 | abhishek kushwaha | Growth | Recruit 5 traders for MetaAPI testing | Not Started | UAT help | sunish runs sessions
W2 | abhishek kushwaha | Growth | Weekly growth report #1 | Not Started | Visibility | aaradhya PostHog access
W2 | ishit | Content | Publish 3 blogs | Not Started | Organic | SEO meta by aaradhya
W2 | ishit | Content | MT5 connect guide + welcome emails | Not Started | Activation | Email send config if needed
W2 | ishit | Content | 1 product Short/Reel | Not Started | Awareness | None
W3 | abhishek kushwaha | Growth | Invite campaign for first 20 beta users | Not Started | Activated users | abhishek allowlist
W3 | ishit | Content | Risk guide + testimonials | Not Started | Trust | None
W4 | abhishek kushwaha | Growth | Expand to 50 + referral messaging | Not Started | Growth | None
W4 | ishit | Content | 3 Shorts: dashboard, coach, MT5 | Not Started | Views | None
Ongoing | abhishek kushwaha | Cadence | 2h outreach · 2h campaigns · 1h community · 1h competitor · 1h reporting · 1h coord | Not Started | Acquisition | None
Ongoing | ishit | Cadence | 3h writing · 2h social · 1h website copy · 1h FAQ/brand | Not Started | Content engine | Hands copy to aaradhya

## Website Checklist
Page | Exists | Eng Owner | Content Owner | Content Ready | SEO/Code Ready | Prod Live | Priority | Notes
/ | Yes | aaradhya | ishit | Partial | Yes | Yes | Critical | Live 200; LCP median 3.93s PASS @ web-00074-nkc; cookie banner live. Hero full ishit copy residual. 2026-08-02
/pricing | Yes | aaradhya | ishit | Partial | Yes | Yes | Critical | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/about | Yes | aaradhya | ishit | Partial | Yes | Yes | Medium | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/blog + slugs | Yes | aaradhya | ishit | Not Started | Yes | Yes | Critical | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/guides + slugs | Yes | aaradhya | ishit | Not Started | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/brokers + slugs | Yes | aaradhya | ishit | Partial | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/login /register /verify | Yes | aaradhya | — | Yes | Yes | Yes | Critical | OTP auth polish + secure cookies code done. Safari device video residual. 2026-08-02
/onboarding | Yes | aaradhya | ishit | Partial | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/dashboard + trading UI | Yes | aaradhya | ishit | Partial | Yes | Yes | Critical | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial. Backend = sunish
/billing /wallet | Yes | aaradhya | abhishek kushwaha | Partial | Yes | Yes | Critical | Billing UI/trial UX shipped to prod web-00074-nkc. Stripe human UAT residual. 2026-08-02
/alpha-coach | Yes | aaradhya | ishit | Partial | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial. Coach API = sunish
/help /docs | Yes | aaradhya | ishit | Partial | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
/legal pages | Yes | aaradhya | abhishek | Yes | Yes | Yes | High | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial. Sign-off
/status | Yes | aaradhya | — | Yes | Yes | Yes | Critical | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial. Live 200 www.profytron.com/status — 2026-07-30
/contact /community /press | Yes | aaradhya | ishit | Partial | Yes | Yes | Medium | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial.
sitemap/robots | Yes | aaradhya | — | Yes | Yes | Yes | Critical | FE eng closeout 2026-08-02; prod web-00074-nkc. Content owner still ishit where Partial. robots.txt + sitemap.xml HTTP 200 — 2026-07-30

## Day_by_Day_1-45
Day | Date | Weekday | Phase | Daily Focus | abhishek (All-Rounder) | sunish (Eng Infra/Trading) | aaradhya (Eng Frontend) | abhishek kushwaha (Growth) | ishit (Content) | End-of-Day Deliverable | Status
1 | 2026-07-21 | Tue | W1 — Stabilize (M0) | Launch OS kickoff + marketing zero baseline | Kickoff: lock Day1–45 plan, approve GCP as primary host, share access (GSC/PostHog/Discord later) | Inventory prod: health probes, Cloud Run services, env secrets checklist | Audit landing LCP causes; list heavy 3D/motion to lazy-load; check /status route locally ¦ FE DONE 2026-08-02 (repo+prod deploy) | START FROM ZERO: create acquisition tracker sheet; define ICP (trader personas); list 20 communities to join | START FROM ZERO: brand voice 1-pager; collect product facts/screenshots needed; competitor homepage swipe file | Prod inventory reports 2026-07-21/22; team kickoff path started | Completed
2 | 2026-07-22 | Wed | W1 — Stabilize (M0) | API path chosen; LCP work started; marketing foundations | Decide Render decommission date; review sunish deploy plan; set SEV1 owner = you | Deploy/fix API on GCP Cloud Run (min-instances=1); document URLs | Start LCP PR: dynamic import hero visuals; defer non-critical JS ¦ FE DONE 2026-08-02 (repo+prod deploy) | Join 5 trader communities (read-only); start prospect CRM columns (name, channel, status) | Outline homepage hero angles (3 options); draft positioning bullets for growth | GCP API path + startupProbe /ready harden (PRODUCTION_STATUS) | Completed
3 | 2026-07-23 | Thu | W1 — Stabilize (M0) | M0 progress + first marketing assets | Verify /health with sunish; unblock secrets if missing | Fix API health until /live /ready /health = 200 for hours; enable basic uptime ping | Continue LCP; measure mobile Lighthouse before/after ¦ FE DONE 2026-08-02 (repo+prod deploy) | Build prospect list to 25 (LinkedIn/Twitter/Telegram leads) | Draft homepage H1 + subhead + CTA (v1); send to abhishek for approve | API /live /ready /health 200; uptime check created 2026-07-23 | Completed
4 | 2026-07-24 | Fri | W1 — Stabilize (M0) | Infra hardening + copy implementation | Approve homepage copy v1; review aaradhya LCP PR | Cloud SQL backups ON; remove/disable duplicate DB instance; rotate critical secrets plan | Implement approved hero copy in code; ship /status page to staging/prod ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 40; start competitor teardown notes (pricing, CTAs, claims) | Draft pricing page messaging; start blog outline #1 What is Copy Trading | Unused Cloud SQL stopped; prod backups ON; secret rotation PLAN only | Completed
5 | 2026-07-25 | Sat | W1 — Stabilize (M0) | Monitoring + content engine start | Wire Search Console property (or grant access); weekly goals check-in 30m | Wire Sentry DSN (API); confirm EXPOSE_DEV_OTP=false; SPF/DKIM checklist start | Wire Sentry web DSN; PostHog provider check; meta/title audit list for public pages ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 55; 5 warm DMs (no pitch spam — value first) | Blog #1 full draft; social calendar skeleton (12 slots empty→fill 4) | Sentry API verified; EXPOSE_DEV_OTP OFF; email DNS -> Day 6 verified | Completed
6 | 2026-07-26 | Sun | W1 — Stabilize (M0) | Weekend push: email + content | Saturday review: blockers log; approve blog #1 direction | Email domain DNS (SPF/DKIM/DMARC) with Resend; test OTP email to yourself | Mobile QA pass on home/pricing/login; fix obvious layout bugs ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 70; competitor teardown doc finished | Revise blog #1; draft LinkedIn post #1 from blog; pricing copy v1 | Resend domain verified; OTP email delivered (Day 6). Marketing — no evidence | Completed
7 | 2026-07-27 | Mon | W1 — Stabilize (M0) | W1 close | Sunday light: update Executive Dashboard; plan Week 2 UAT order | Rest / on-call only OR finish health if still red | Rest / merge LCP PR if ready ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 80; rest of day light research | Rest / polish social calendar to 8 posts planned | W1 infra mostly green. Marketing >0 assets — NO evidence | Partial — aaradhya FE eng complete 2026-08-02
8 | 2026-07-28 | Tue | W2 — Prove live (M1–M4) | UAT day 1 + first publish prep | Declare UAT week; order: OTP → Payments → MetaAPI; assign evidence folder | Live OTP UAT formal (ALLOW_LIVE_EMAIL_OTP); file evidence | SEO code: robots/sitemap verify on prod; fix broken meta tags ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 90; Discord/Telegram channel CREATE (empty ok) | Blog #1 FINAL for publish; start blog #2 MT5 Automation outline | Formal live OTP UAT PASS (D7_OTP_UAT_20260728). Payment audit Day 8 (no live checkout). | Completed
9 | 2026-07-29 | Wed | W2 — Prove live (M1–M4) | Payments UAT + first SEO content live | Review OTP evidence; unblock payment keys if needed | Live payment UAT (Stripe OR Razorpay) + webhook entitlement proof | Implement pricing page copy; billing UI polish from growth notes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 100 (TARGET); tag top 30 for beta invite later | Publish blog #1 live; draft blog #2 | Trial RC + Medium fixes (local). Live Payments UAT OPEN. Blog publish — NO evidence. | Partial — aaradhya FE eng complete 2026-08-02
10 | 2026-07-30 | Thu | W2 — Prove live (M1–M4) | MetaAPI UAT + distribution | Join MetaAPI UAT session; note product gaps | Live MetaAPI MT5 connect UAT; sync → dashboard balance check | Connected-accounts empty states; Safari login QA ¦ FE DONE 2026-08-02 (repo+prod deploy) | Recruit 2 trader friends for tomorrow's broker test; community channel rules pinned | Blog #2 draft; LinkedIn/X post announcing blog #1 | TODAY: Trial race-condition fix validated locally. MetaAPI/Get Bots UAT OPEN. Sheet sync applied. | Partial — aaradhya FE eng complete 2026-08-02
11 | 2026-07-31 | Fri | W2 — Prove live (M1–M4) | Coach live + outreach starts | Coach Insights admin check; decide beta allowlist draft emails (internal) | AI Coach live keys test; Coach Insights migration confirm | Alpha Coach UI empty states; help page structure for FAQs later ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach email #1–3 (brokers/creators) | Blog #2 revise; start blog #3 AI Coach outline; social post #2 | Coach stream works; 3 outreach emails | Partial — aaradhya FE eng complete 2026-08-02
12 | 2026-08-01 | Sat | W2 — Prove live (M1–M4) | W2 ship day | Friday deploy window approve; W2 review 45m | Stabilize any UAT bugs; uptime alert test fire | Ship remaining SEO fixes; Lighthouse re-measure home mobile ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach #4–6; invite 10 people to Discord (soft) | Publish blog #2; FAQ list of 15 topics drafted | LCP improved number recorded; blog #2 live | Partial — aaradhya FE eng complete 2026-08-02
13 | 2026-08-02 | Sun | W2 — Prove live (M1–M4) | Hardening + content | Saturday: legal pages skim for sign-off gaps | Wallet smoke test; rate-limit smoke on login/register | Cookie/banner check; OG images brief from ishit assets ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect CRM hygiene; note replies from outreach | Blog #3 draft; write 3 FAQ answers | Security smokes; FAQ started | Partial — aaradhya FE eng complete 2026-08-02
14 | 2026-08-03 | Mon | W2 — Prove live (M1–M4) | W2 close — M1–M4 largely green | Sunday: update Launch Countdown statuses; plan dogfood cohort of 5 | Rest / critical bugs only | Rest / critical UI only ¦ FE DONE 2026-08-02 (repo+prod deploy) | Light: community engagement 30m | Publish blog #3 OR schedule Mon; social posts #3–4 written | 3 blogs path complete; UAT evidence pack | Partial — aaradhya FE eng complete 2026-08-02
15 | 2026-08-04 | Tue | W3 — Dogfood + beta prep (M5) | Dogfood starts; invite copy ready | Internal dogfood kickoff: invite 5 (team+friends); set feedback form | Support dogfood: fix P0 bugs from day; paper trading path check | Onboarding flow polish; risk page UX ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prepare invite email list (20 names from top prospects); Discord onboarding message | Write beta invite email copy + welcome email #1 | 5 dogfood users active | Partial — aaradhya FE eng complete 2026-08-02
16 | 2026-08-05 | Wed | W3 — Dogfood + beta prep (M5) | Bug burn-down + email sequence | Triage dogfood feedback; prioritize P0/P1 board | P0 backend fixes (sync/auth/payments leftovers) | P0 frontend fixes from dogfood ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach #7–10; soft ask for beta interest | Welcome email #2–3 copy; MT5 connect guide outline | P0 list shrinking; welcome sequence drafted | Partial — aaradhya FE eng complete 2026-08-02
17 | 2026-08-06 | Thu | W3 — Dogfood + beta prep (M5) | Allowlist + beta shortlist | Set BETA_ALLOWLIST_EMAILS for dogfood→beta; legal sign-off schedule | Allowlist wiring verify; notification emails for beta | Community page CTAs + Discord links live on site ¦ FE DONE 2026-08-02 (repo+prod deploy) | Confirm 20 beta candidates verbally/DM; track yes/maybe/no | Write MT5 connect guide draft; 5 more FAQ answers | Allowlist live; 20 candidates contacted | Partial — aaradhya FE eng complete 2026-08-02
18 | 2026-08-07 | Fri | W3 — Dogfood + beta prep (M5) | Legal + DR + help content | Legal sign-off Privacy/Terms/Risk (or lawyer note) | Backup restore drill (record date in docs) | Help center page updates for top FAQs (implement ishit text) ¦ FE DONE 2026-08-02 (repo+prod deploy) | India GTM notes (Razorpay messaging); growth report template | Finalize MT5 guide; social post #5–6 | Legal signed; restore dated | Partial — aaradhya FE eng complete 2026-08-02
19 | 2026-08-08 | Sat | W3 — Dogfood + beta prep (M5) | Beta-ready checkpoint | Friday: dogfood retro; GO/NO-GO for Mon beta invites | Copy-trading subscribe dry-run on staging/prod | Dashboard polish from dogfood notes; mobile pass ¦ FE DONE 2026-08-02 (repo+prod deploy) | First weekly growth report (prospects, replies, channel size) | Publish MT5 guide; FAQ pack 10/15 done | GO decision for M6 | Partial — aaradhya FE eng complete 2026-08-02
20 | 2026-08-09 | Sun | W3 — Dogfood + beta prep (M5) | Invite ammo ready | Saturday: finalize invite list of 20 + backups 10 | Light: bot marketplace smoke | Light: publish any pending UI ¦ FE DONE 2026-08-02 (repo+prod deploy) | Personalize 20 invite notes (not blast) | Invite email FINAL; social teaser (no public spam) | 20 personalized invites queued | Partial — aaradhya FE eng complete 2026-08-02
21 | 2026-08-10 | Mon | W3 — Dogfood + beta prep (M5) | W3 close | Sunday rest / emergency only; emotional prep for beta week | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest / community light | Rest / schedule Mon send | Ready for closed beta | Partial — aaradhya FE eng complete 2026-08-02
22 | 2026-08-11 | Tue | W4 — Closed beta 20 (M6) | M6 — beta invites out | SEND 20 beta invites; monitor support channel personally 2h | On-call for signup/OTP/broker issues; hotfix ready | On-call UI; watch registration funnel in PostHog ¦ FE DONE 2026-08-02 (repo+prod deploy) | DM follow-ups to non-openers; welcome in Discord | Post 'beta welcome' content inside community only | 20 invites sent | Partial — aaradhya FE eng complete 2026-08-02
23 | 2026-08-12 | Wed | W4 — Closed beta 20 (M6) | Activation day | Track activation: who connected broker; unblock manually | MetaAPI issues triage for beta users | Onboarding drop-off fixes if funnel shows pain ¦ FE DONE 2026-08-02 (repo+prod deploy) | Help 5 users activate; log objections | Publish 2 FAQs that beta asked; social educational post | Broker-connect count rising | Partial — aaradhya FE eng complete 2026-08-02
24 | 2026-08-13 | Thu | W4 — Closed beta 20 (M6) | Listen + fix | Product calls with 3 beta users (15m each) | Fix top sync/balance bug from beta | Fix top UI confusion from beta ¦ FE DONE 2026-08-02 (repo+prod deploy) | Invite 5 more from waitlist if slots; partnership update | Case-study notes (with consent); Short/Reel script #1 | 3 interviews done | Partial — aaradhya FE eng complete 2026-08-02
25 | 2026-08-14 | Fri | W4 — Closed beta 20 (M6) | Content from real users | Update roadmap from interviews; kill 1 non-critical feature idea | Coach quality issues / tool failures triage | Empty-state + copy tweaks from ishit ¦ FE DONE 2026-08-02 (repo+prod deploy) | Community engagement challenge (share first win) | Record Short #1 (dashboard or coach); FAQ 15/15 | Short #1 recorded; FAQ complete | Partial — aaradhya FE eng complete 2026-08-02
26 | 2026-08-15 | Sat | W4 — Closed beta 20 (M6) | W4 metrics | Friday beta metrics review (activation %, SEV1=0?) | Stabilize; no risky deploys after 4pm | Ship FAQ page updates; CWV check ¦ FE DONE 2026-08-02 (repo+prod deploy) | Weekly growth report #2; referral ask to activated users | Publish Short #1; LinkedIn story from beta learnings (anonymized) | Activation rate logged | Partial — aaradhya FE eng complete 2026-08-02
27 | 2026-08-16 | Sun | W4 — Closed beta 20 (M6) | Support + nurture | Saturday: deep user support hour | P1 bugfixes | P1 UI fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Nurture maybe→yes prospects | Guide: Risk management draft start | P1 burn-down | Partial — aaradhya FE eng complete 2026-08-02
28 | 2026-08-17 | Mon | W4 — Closed beta 20 (M6) | W4 close — 20-user beta running | Sunday: plan expand-to-50 criteria | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Risk guide outline done | M6 achieved if ≥10 activated | Partial — aaradhya FE eng complete 2026-08-02
29 | 2026-08-18 | Tue | W5 — Expand toward 50 (M7) | Scale invites | Approve next 30 invites; set activation target >30% | Copy-trading + bots UAT leftovers for power users | Instrument time-to-first-broker events if missing ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send next invite wave (15) | Publish risk management guide | 35 total invited path | Partial — aaradhya FE eng complete 2026-08-02
30 | 2026-08-19 | Wed | W5 — Expand toward 50 (M7) | Insights-driven eng | Coach Insights weekly ritual #1 | Improve coach responses for top thumbs-down intents | Analytics pages UX polish if users care ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send invite wave (15 more) → ~50 invited | Social posts #7–8; reply to all comments | ~50 invites out | Partial — aaradhya FE eng complete 2026-08-02
31 | 2026-08-20 | Thu | W5 — Expand toward 50 (M7) | Partnerships + perf | Partnership close calls (2) | Performance: API slow endpoints from beta usage | Frontend performance on dashboard ¦ FE DONE 2026-08-02 (repo+prod deploy) | Creator/broker collab draft agreement notes | Case study draft v1 (1 user) | 2 partner calls | Partial — aaradhya FE eng complete 2026-08-02
32 | 2026-08-21 | Fri | W5 — Expand toward 50 (M7) | Retention focus | Review churn/inactive beta users; win-back plan | Notification reliability (trade alerts email) | Settings/support ticket UX ¦ FE DONE 2026-08-02 (repo+prod deploy) | Win-back DMs to inactive; community AMA announce | AMA announcement creative; Short #2 script | Win-back started | Partial — aaradhya FE eng complete 2026-08-02
33 | 2026-08-22 | Sat | W5 — Expand toward 50 (M7) | Community proof | Friday: 50-user checkpoint vs activation KPI | Bugfix day from AMA prep | Ship pending UI; prepare demo environment ¦ FE DONE 2026-08-02 (repo+prod deploy) | Host community AMA / office hours | Record Short #2 during/after AMA | AMA done; activation % reported | Partial — aaradhya FE eng complete 2026-08-02
34 | 2026-08-23 | Sun | W5 — Expand toward 50 (M7) | Content + fixes | Saturday support coverage | P1 fixes | P1 fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Follow-ups from AMA | Publish Short #2; polish case study | Case study near-final | Partial — aaradhya FE eng complete 2026-08-02
35 | 2026-08-24 | Mon | W5 — Expand toward 50 (M7) | W5 close | Sunday: plan load-test week; declare M7 status | Rest / prepare load test env | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Rest / schedule posts | M7: toward 50 activated trajectory | Partial — aaradhya FE eng complete 2026-08-02
36 | 2026-08-25 | Tue | W6 — Harden + load (M8) | Load test day | Authorize load test window; freeze feature work (bugs only) | Run k6 load:d7:100 against healthy API; capture report | Fix frontend errors under load if any; monitor RUM ¦ FE DONE 2026-08-02 (repo+prod deploy) | No big campaigns (stability week); nurture only | Publish case study; educational posts only | Load report attached | Partial — aaradhya FE eng complete 2026-08-02
37 | 2026-08-26 | Wed | W6 — Harden + load (M8) | Perf fixes | Review load failures; prioritize fixes | Fix load bottlenecks (DB/redis/timeouts) | Reduce chatty client polling if found ¦ FE DONE 2026-08-02 (repo+prod deploy) | Quiet growth: 5 high-quality invites only | Blog refresh/internal links pass with aaradhya notes | p95 improved | Partial — aaradhya FE eng complete 2026-08-02
38 | 2026-08-27 | Thu | W6 — Harden + load (M8) | M8 evidence | Re-run load test subset; backup drill if not done | Second load pass OR restore drill evidence | SEO internal linking code; image alts ¦ FE DONE 2026-08-02 (repo+prod deploy) | Referral program messaging soft launch to beta | 2 posts on referral/value; FAQ updates | Load pass or clear gap list | Partial — aaradhya FE eng complete 2026-08-02
39 | 2026-08-28 | Fri | W6 — Harden + load (M8) | Security week | Security checklist D2 review with sunish | Secret rotation remaining; security Playwright suite | Security-sensitive UI (API keys settings) review ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership pipeline update doc | Trust content: risk disclosure explainer social | D2 checklist advanced | Partial — aaradhya FE eng complete 2026-08-02
40 | 2026-08-29 | Sat | W6 — Harden + load (M8) | M8 checkpoint | Friday: GO/NO-GO for push to 100 | Stabilize; document runbooks gaps closed | Status page polish; public trust signals ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prepare 50 more prospect outreaches for next week | Content calendar for scale week | GO for M9 or fix list | Partial — aaradhya FE eng complete 2026-08-02
41 | 2026-08-30 | Sun | W6 — Harden + load (M8) | Prep scale | Saturday: ops dry-run of invite-to-100 process | Light fixes | Light fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Segment prospect list for 100 | Batch social assets | Invite ops ready | Partial — aaradhya FE eng complete 2026-08-02
42 | 2026-08-31 | Mon | W6 — Harden + load (M8) | W6 close | Sunday rest | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Rest | M8 ideally green | Partial — aaradhya FE eng complete 2026-08-02
43 | 2026-09-01 | Tue | W7 — Scale to 100 (M9) | Scale start | Open scale: approve invites toward 100 users | Capacity watch; auto-scale/min instances tune | Funnel UX final polish for new users ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send large invite wave (batch 1 of 2) | Launch content burst: 1 blog remix + 3 socials | User count climbing | Partial — aaradhya FE eng complete 2026-08-02
44 | 2026-09-02 | Wed | W7 — Scale to 100 (M9) | Push to 100 | Daily activation standup 15m; unblock stuck users | Hotfixes only; MetaAPI quotas watch | Hotfixes only; onboarding tweaks ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send batch 2 invites; partnerships announce if ready | User-story posts (consented); Short #3 | ~100 invited / approaching 100 active | Partial — aaradhya FE eng complete 2026-08-02
45 | 2026-09-03 | Thu | W7 — Scale to 100 (M9) | 45-day finish line | DAY 45 REVIEW: score M0–M9; decide open growth vs stay closed; update sheet | Write eng retro: what broke, what held; next 30d eng backlog | Write web/UX retro; CWV final numbers ¦ FE DONE 2026-08-02 (repo+prod deploy) | Growth retro: CAC proxy, best channels, next 30d acquisition plan | Content retro: top posts; next 30d editorial calendar | Written retros + 100-user status + next plan | Partial — aaradhya FE eng complete 2026-08-02

## Executive Dashboard (1)
PROFYTRON — EXECUTIVE DASHBOARD
Updated 2026-07-20 · abhishek = all-rounder · Coding = sunish + aaradhya · Marketing = abhishek kushwaha + ishit
Metric | Value |  | Team Member | Role | Open Tasks | Est Hours
Total Tasks | 97 |  | abhishek | CEO / All-Rounder | 17 | 118
Completed | 0 |  | sunish | Eng — Infra/Trading/AI | 29 | 175
In Progress | 4 |  | aaradhya | Eng — Frontend/Web | 21 | 119
Blocked | 2 |  | abhishek kushwaha | Marketing — Growth | 10 | 121
Not Started | 86 |  | ishit | Marketing — Content | 15 | 113
Deferred | 5
Remaining (excl deferred) | 92
Est hours active | 646
WHO DOES WHAT (CORRECTED)
abhishek — All-Rounder (Product lead + can code/review/ops anytime)
Priorities, beta, legal, partnerships, GSC/allowlist, PR reviews, incident response, fills gaps
sunish — Engineering (Infra, Trading, AI, Backend)
GCP, MetaAPI, bots, coach backend, payments/auth UAT, security, load tests, Sentry, DB backups
aaradhya — Engineering (Frontend, Web, Product UI)
Landing LCP, /status, onboarding, dashboard UI, SEO code, PostHog, billing UI, Safari auth, marketing page impl
abhishek kushwaha — Marketing Growth (NO coding)
Acquisition, partnerships, invites, community, campaigns, prospect lists, competitor intel
ishit — Marketing Content (NO coding)
Blogs, guides, social, website copy, brand, email copy, FAQs, Shorts
LAUNCH READINESS
Area | Status | Next Action | Owner
Website code / LCP | Partial | Ship LCP + /status | aaradhya
Website copy | Not Started | Hero + pricing + blogs | ishit
Auth live OTP | Blocked | UAT after API up | sunish
Payments live | Blocked | Checkout UAT | sunish
MetaAPI live | Blocked | MT5 UAT | sunish
AI Coach | Partial | Keys + UI polish + content | sunish / aaradhya / ishit
Infrastructure | Blocked | GCP API stable | sunish (+ abhishek)
Acquisition | Not Started | 100 prospects + Discord | abhishek kushwaha
Closed beta | Not Started | Allowlist + invites | abhishek
TOP 3 BLOCKERS
1. Production API up — sunish (abhishek reviews)
2. Live UAT OTP + Payments + MetaAPI — sunish
3. Web ready (LCP+/status) + marketing engine (prospects + copy) — aaradhya + kushwaha + ishit
RULE: Coding = sunish + aaradhya (+ abhishek as all-rounder). Marketing-only = abhishek kushwaha + ishit.

## Daily 10h Tasks
Day | Date | Weekday | Phase | Person | Role | Block | Start | End | Hours | Task (do this today) | Done when (EOD proof) | Done? (Y/N) | Notes
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Open Day-by-Day sheet. Walk team through Day 1–7 out loud (15–20 min standup). | Everyone knows today's EOD
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Decide: GCP Cloud Run is primary API host. Write it in Deployment Tracker + RUNBOOK draft. | Decision written, Render marked deprecate | Y | GCP chosen; risks reviewed via audits
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Make access checklist: who needs GCP, Vercel/web, Resend, Stripe/Razorpay, MetaAPI, PostHog, GSC. | Checklist shared in group chat
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Draft 1-page ICP: who we invite first (India retail traders? prop? creators?). | ICP doc in Drive/Notion
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review last health-probe notes (2026-07-19). List top 5 eng risks with sunish. | Risk list of 5 | Y | GCP chosen; risks reviewed via audits
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: collect screenshots/links of what each person finished. Mark Day 1 status. | Day 1 row updated
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. Confirm GCP project + billing account access works. | Can open Cloud Console
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Hit current prod /live /ready /health. Save raw responses + timestamps. | Probe log file saved | Y | Evidence: prod inventory 2026-07-21/22
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 12:00 | 14:00 | 2 | List all running services (Cloud Run/Render/Vercel). Mark primary vs legacy. | Inventory table | Y | Evidence: prod inventory 2026-07-21/22
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Diff env vars vs .env.example for API. Note missing secrets. | Missing-secrets list | Y | Evidence: prod inventory 2026-07-21/22
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 16:00 | 18:00 | 2 | Draft deploy commands for API (gcloud builds submit / Cloud Run). | Command sheet
1 | 2026-07-21 | Tue | W1 Stabilize | sunish | Eng — Infra/Trading | 6 | 18:00 | 19:00 | 1 | EOD: post inventory + probe results in group chat. | Posted | Y | Evidence: prod inventory 2026-07-21/22
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. Confirm repo runs locally (pnpm web). | Dev server up | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Profile landing: list heavy components (3D, motion, images). Write hit-list with KB/ms guesses. | Hit-list doc | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Open /status locally. Note what breaks without API. | Notes | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Grab mobile screenshots of home at 390px. Mark clutter. | Screenshots folder | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Sync with ishit on what copy will change soon. | Aligned | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD post hit-list. | Posted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Accept: marketing starts at zero today. | Mindset set
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 12:00 | 2 | Create prospect CRM (Sheets): Name, Channel, Link, Status, Notes, Next action. | CRM exists
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 12:00 | 14:00 | 2 | Write ICP in plain words (who buys, who wastes time). | ICP paragraph
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | List 20 places traders hang out (TG/Discord/Reddit/LinkedIn/YouTube). | List of 20
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 18:00 | 2 | Join 5 communities. Set notifications. Do not pitch today. | Joined 5
1 | 2026-07-21 | Tue | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 18:00 | 19:00 | 1 | EOD: screenshot CRM empty template filled with 3 sample rows. | Done
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. Marketing content starts at zero — no fake 'already posted'. | Clear
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Write brand voice 1-pager: words we use / words we avoid (no fake ROI promises). | Voice doc
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 3 | 12:00 | 14:00 | 2 | List screenshots/facts you need from eng/product. Ping them once. | Ask list sent
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 17:00 | 3 | Competitor homepage swipe file: 5 screenshots + what you like/hate. | Swipe file
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 5 | 17:00 | 18:00 | 1 | Draft 3 directions for homepage H1 (just headlines). | 3 headlines
1 | 2026-07-21 | Tue | W1 Stabilize | ishit | Marketing — Content | 6 | 18:00 | 19:00 | 1 | EOD share voice doc + headlines. | Shared
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup 15m. Unblock secrets/logins people are missing. | No one blocked on access
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Sit with sunish on Cloud Run deploy plan. Approve env vars list. | Env var list signed off | Y | API path approved/executed
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Review aaradhya's LCP hit-list (which components are heavy). | Approve what to cut/lazy-load
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Write positioning bullets (what Profytron is / isn't) for ishit + growth. | Half-page positioning
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Partner/investor light admin OR reply pending emails. | Inbox cleared of >2 day old
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD check: API deploy attempt status + LCP PR opened? | Yes/No logged
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Deploy/fix API on Cloud Run with min-instances=1. Watch logs. | Revision deployed or error captured | Y | API on Cloud Run min-instances=1
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 13:00 | 15:00 | 2 | Map custom domain / DNS if needed for API URL. | DNS note
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Set memory/CPU and concurrency sane defaults. Document why. | Settings documented
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | Smoke: curl health endpoints from your laptop + phone network if possible. | Results noted | Y | API on Cloud Run min-instances=1
2 | 2026-07-22 | Wed | W1 Stabilize | sunish | Eng — Infra/Trading | 6 | 17:00 | 18:00 | 1 | EOD message: up or still down, with exact URL. | Posted | Y | API on Cloud Run min-instances=1
2 | 2026-07-22 | Wed | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
2 | 2026-07-22 | Wed | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 14:00 | 4 | Start LCP PR: dynamic import / lazy heavy hero visuals. | PR opened | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
2 | 2026-07-22 | Wed | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 14:00 | 16:00 | 2 | Remove or defer non-critical third-party scripts on home if any. | Change committed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
2 | 2026-07-22 | Wed | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 16:00 | 18:00 | 2 | Run Lighthouse mobile locally. Save JSON/screenshot. | Before metrics saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
2 | 2026-07-22 | Wed | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 18:00 | 19:00 | 1 | EOD: paste before LCP number in chat. | Number shared | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Add 15 real prospects to CRM (real profiles, not fake). | 15 rows
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Read 2 competitor landing pages. Note CTA + pricing claims. | Notes doc
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Draft first touch DM template (helpful, not salesy). Get abhishek OK. | Template approved
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Engage 3 community posts with genuine answers. | 3 comments
2 | 2026-07-22 | Wed | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD CRM count. | Count posted
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Expand best H1 into full hero: H1, subhead, CTA, microcopy. | Hero draft v1
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Positioning bullets from abhishek → turn into plain user language. | Bullets rewritten
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Start swipe → messaging do/don't list. | List
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Collect asset needs (chart mock, logo, broker UI). | List
2 | 2026-07-22 | Wed | W1 Stabilize | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send hero to abhishek. | Sent
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup. If API still red, make it today's only eng priority. | Priority locked | Y | API healthy
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Pair on /health with sunish until it returns 200 (or document exact error). | 200 OK or written blocker | Y | API healthy
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Approve homepage H1/subhead options from ishit (pick 1). | Copy choice locked
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Start Search Console setup OR request ownership verification DNS. | GSC property created/pending
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Review prospect ICP with kushwaha — quality over vanity numbers. | Agree what 'good lead' means
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD log + tomorrow UAT prep note. | Note saved
3 | 2026-07-23 | Thu | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. If health != 200, cancel other work. | Focus locked | Y | Health 200 + uptime check 2026-07-23
3 | 2026-07-23 | Thu | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Debug until /health is 200 for 30+ continuous minutes. | Stable 200 or root cause written | Y | Health 200 + uptime check 2026-07-23
3 | 2026-07-23 | Thu | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Add simple uptime ping (cron/UptimeRobot/GCP monitoring). | Ping configured | Y | Health 200 + uptime check 2026-07-23
3 | 2026-07-23 | Thu | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Start Cloud SQL backup enablement checklist. | Checklist half done | Y | Health 200 + uptime check 2026-07-23
3 | 2026-07-23 | Thu | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD screenshot of green health. | Screenshot saved | Y | Health 200 + uptime check 2026-07-23
3 | 2026-07-23 | Thu | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
3 | 2026-07-23 | Thu | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 14:00 | 4 | Continue LCP PR until Lighthouse improves vs yesterday. | After metrics ≥ better | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
3 | 2026-07-23 | Thu | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 14:00 | 16:00 | 2 | Wire homepage to use approved copy when abhishek picks it (or feature-flag). | Copy hooked or waiting | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
3 | 2026-07-23 | Thu | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 16:00 | 18:00 | 2 | Fix 2 mobile CSS issues you saw Day 1. | 2 fixes merged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
3 | 2026-07-23 | Thu | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 18:00 | 19:00 | 1 | EOD metrics update. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | CRM → 30 prospects. Quality check with abhishek definition. | 30 rows
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Send 5 warm DMs using approved template. | 5 DMs
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Track replies in CRM same day. | Statuses updated
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Competitor teardown: pricing section notes. | Notes
3 | 2026-07-23 | Thu | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
3 | 2026-07-23 | Thu | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. Apply abhishek feedback on hero. | Edits
3 | 2026-07-23 | Thu | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Hero copy v1 FINAL candidate. | Final candidate
3 | 2026-07-23 | Thu | W1 Stabilize | ishit | Marketing — Content | 3 | 13:00 | 16:00 | 3 | Blog #1 outline: What is Copy Trading (H2s, examples, CTA). | Outline
3 | 2026-07-23 | Thu | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Start social calendar sheet: 12 rows date/channel/idea. | Calendar skeleton
3 | 2026-07-23 | Thu | W1 Stabilize | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup 15m + unblock access. | Standup done
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Shadow eng on the critical path (API or LCP). Take notes, remove blockers. | Blocker removed or escalated
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Review and comment on PRs / deploy notes. | At least 1 review done
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Work ICP/positioning or GSC/DNS admin. | Artifact updated
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Reply growth questions on messaging. | Answers sent
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD: update Launch Countdown status. | Countdown updated
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Turn ON Cloud SQL / Neon backups. Kill or stop duplicate unused DB if safe. | Backups ON evidence | Y | Day 4: backups ON, unused STOPPED, rotation PLAN
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 13:00 | 15:00 | 2 | Draft secret rotation plan (JWT, AES_MASTER_KEY) — don't rotate yet without abhishek. | Plan written | Y | Day 4: backups ON, unused STOPPED, rotation PLAN
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Clean Render free-tier dependency notes; mark decommission date. | Date set | Y | Day 4: backups ON, unused STOPPED, rotation PLAN
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | Help aaradhya if /status needs API fields. | Unblocked or N/A
4 | 2026-07-24 | Fri | W1 Stabilize | sunish | Eng — Infra/Trading | 6 | 17:00 | 18:00 | 1 | EOD Deployment Tracker update. | Updated | Y | Day 4: backups ON, unused STOPPED, rotation PLAN
4 | 2026-07-24 | Fri | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
4 | 2026-07-24 | Fri | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Implement approved hero copy in code. Ship. | Live or PR merged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
4 | 2026-07-24 | Fri | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 13:00 | 16:00 | 3 | Deploy /status to prod/staging. Verify URL. | /status not 404 | Y | /status live 200 on www 2026-07-30
4 | 2026-07-24 | Fri | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Basic status page polish (last checked time if easy). | Polish done or skipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
4 | 2026-07-24 | Fri | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD share /status URL. | Shared | Y | /status live 200 on www 2026-07-30
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | CRM → 40. Add brokers/creators tab separately. | 40 + creators tab
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Finish competitor teardown 1-pager for ishit/aaradhya. | 1-pager shared
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Send 5 more DMs. Follow up yesterday's non-replies once. | Touches done
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Short sync with ishit on what claims we can legally make. | Aligned
4 | 2026-07-24 | Fri | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
4 | 2026-07-24 | Fri | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
4 | 2026-07-24 | Fri | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Pricing page messaging draft (plan names explanations, objections). | Pricing draft
4 | 2026-07-24 | Fri | W1 Stabilize | ishit | Marketing — Content | 3 | 12:00 | 16:00 | 4 | Blog #1 full draft (800–1200 words, human, no fluff). | Full draft
4 | 2026-07-24 | Fri | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Fill 4 social calendar slots with real captions. | 4 captions
4 | 2026-07-24 | Fri | W1 Stabilize | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | EOD drafts to abhishek/growth for fact check. | Sent
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup. | Done
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Secrets/DNS/email domain decisions with sunish. | Decision written
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Approve website copy v1 from ishit. | Approved or redlines
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Competitive skim + notes for growth. | 5 bullets
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Ops: who owns SEV1 tonight? | On-call named
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD checklist tick. | Day closed
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Wire Sentry DSN for API. Force a test error. Confirm event arrives. | Sentry event seen | Y | Day 5/6: Sentry + OTP flag + email path
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 12:00 | 14:00 | 2 | Confirm EXPOSE_DEV_OTP is false in prod. Screenshot config. | Confirmed off | Y | Day 5/6: Sentry + OTP flag + email path
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 14:00 | 17:00 | 3 | Start Resend domain: SPF/DKIM records with whoever owns DNS. | Records added or pending | Y | Day 5/6: Sentry + OTP flag + email path
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 17:00 | 18:00 | 1 | Send test OTP to your own email. Note spam vs inbox. | Result logged | Y | Day 5/6: Sentry + OTP flag + email path
5 | 2026-07-25 | Sat | W1 Stabilize | sunish | Eng — Infra/Trading | 6 | 18:00 | 19:00 | 1 | EOD. | Logged
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | Wire Sentry for web. Trigger test error in staging. | Event seen | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 12:00 | 15:00 | 3 | Audit meta title/description on home, pricing, blog index. Spreadsheet gaps. | Gap sheet | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Check PostHog provider env; note what's missing. | Missing env list | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Help ishit with screenshot sizes for blog. | Assets helped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | CRM → 55. Tag A/B/C priority. | Tagged
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Send 8 DMs to A-priority only. | 8 DMs
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Book or attempt 1 coffee chat / call with a trader. | Ask sent
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Log what messaging gets replies. | Learning note
5 | 2026-07-25 | Sat | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Revise blog #1 from feedback. Add internal links plan. | Revised draft
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | LinkedIn/X post draft promoting blog #1 (not clickbait). | Post draft
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Pricing copy v1 polish. | Polished
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Fill 4 more social slots. | 8 total planned
5 | 2026-07-25 | Sat | W1 Stabilize | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
6 | 2026-07-26 | Sun | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
6 | 2026-07-26 | Sun | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
6 | 2026-07-26 | Sun | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
6 | 2026-07-26 | Sun | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
6 | 2026-07-26 | Sun | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
6 | 2026-07-26 | Sun | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
6 | 2026-07-26 | Sun | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
6 | 2026-07-26 | Sun | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
6 | 2026-07-26 | Sun | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
6 | 2026-07-26 | Sun | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
6 | 2026-07-26 | Sun | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
6 | 2026-07-26 | Sun | W1 Stabilize | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup. | Done
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Secrets/DNS/email domain decisions with sunish. | Decision written
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Approve website copy v1 from ishit. | Approved or redlines
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Competitive skim + notes for growth. | 5 bullets
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Ops: who owns SEV1 tonight? | On-call named
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD checklist tick. | Day closed
7 | 2026-07-27 | Mon | W1 Stabilize | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Watch Cloud Run metrics / errors. | No silent fire
7 | 2026-07-27 | Mon | W1 Stabilize | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfixes only for scale week. | Hotfix or idle with monitoring
7 | 2026-07-27 | Mon | W1 Stabilize | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Quota checks MetaAPI / DB connections. | Quotas OK or raised
7 | 2026-07-27 | Mon | W1 Stabilize | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Write eng retro bullets. | Retro bullets
7 | 2026-07-27 | Mon | W1 Stabilize | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD user-load note. | Logged
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Funnel watch. | Noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Hotfix onboarding/UX only. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Final polish CTAs for new invites. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Write web/UX retro bullets. | Retro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV final snapshot. | Saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 11:00 | 2 | CRM → 80. Dedupe names. | 80 clean
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 2 | 11:00 | 13:00 | 2 | Write Week 2 outreach plan (who, which channel). | Plan
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 14:00 | 1 | Light community presence. | 1–2 comments
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 15:00 | 1 | Rest remaining afternoon. | Rested
7 | 2026-07-27 | Mon | W1 Stabilize | abhishek kushwaha | Marketing — Growth | 5 | 15:00 | 19:00 | 4 | Buffer: finish slips, document blockers, update your tracker row, tidy notes. | Tracker updated + blockers written
7 | 2026-07-27 | Mon | W1 Stabilize | ishit | Marketing — Content | 1 | 9:00 | 11:00 | 2 | Light polish only on blog #1. | Ready for Mon publish
7 | 2026-07-27 | Mon | W1 Stabilize | ishit | Marketing — Content | 2 | 11:00 | 13:00 | 2 | Social calendar polish to 8–10. | Ready
7 | 2026-07-27 | Mon | W1 Stabilize | ishit | Marketing — Content | 3 | 13:00 | 14:00 | 1 | Rest writing muscles. | Rested
7 | 2026-07-27 | Mon | W1 Stabilize | ishit | Marketing — Content | 4 | 14:00 | 15:00 | 1 | Optional: FAQ question list brainstorm 15 topics. | 15 topics
7 | 2026-07-27 | Mon | W1 Stabilize | ishit | Marketing — Content | 5 | 15:00 | 19:00 | 4 | Buffer: finish slips, document blockers, update your tracker row, tidy notes. | Tracker updated + blockers written
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: UAT order OTP→Pay→MetaAPI. | Order confirmed
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Witness live UAT; save screenshots into evidence folder. | Evidence files saved
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Unblock API keys / dashboard access for payments or MetaAPI. | Keys available
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Review published blog for factual errors before/after go-live. | Corrections sent
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Short sync with growth on Discord rules. | Rules agreed
8 | 2026-07-28 | Tue | W2 Prove | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD: mark UAT pass/fail in Track D style note. | Pass/fail logged
8 | 2026-07-28 | Tue | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. Freeze risky deploys during OTP UAT. | Freeze noted | Y | Day 7 formal OTP UAT PASS 2026-07-28
8 | 2026-07-28 | Tue | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Formal live OTP UAT. Record steps, codes delivery time, failures. | Evidence markdown/screenshots | Y | Day 7 formal OTP UAT PASS 2026-07-28
8 | 2026-07-28 | Tue | W2 Prove | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Fix any OTP bug found same day if <2h; else ticket P0. | Fixed or P0 filed
8 | 2026-07-28 | Tue | W2 Prove | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Prepare payment keys checklist for tomorrow. | Checklist ready | N | Day 8 audit only — live checkout UAT NOT done
8 | 2026-07-28 | Tue | W2 Prove | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD upload evidence. | Uploaded | Y | Day 7 formal OTP UAT PASS 2026-07-28
8 | 2026-07-28 | Tue | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
8 | 2026-07-28 | Tue | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Verify sitemap.xml + robots.txt on production. Fix code if wrong. | Correct on prod | Y | robots.txt + sitemap.xml 200
8 | 2026-07-28 | Tue | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 16:00 | 3 | Fix meta tags from gap sheet (highest traffic pages first). | ≥3 pages fixed | Y | robots.txt + sitemap.xml 200
8 | 2026-07-28 | Tue | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | JSON-LD quick validate on home. | Valid or issue listed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
8 | 2026-07-28 | Tue | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 12:00 | 2 | CRM → 90. | 90
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 12:00 | 15:00 | 3 | Create Discord OR Telegram beta channel. Add team. Pin rules. | Channel live
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Invite 5 trusted people as seed members (friends/dogfood). | 5 joined
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | No public spam about beta yet. | Respected
8 | 2026-07-28 | Tue | W2 Prove | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD channel link to team. | Shared
8 | 2026-07-28 | Tue | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
8 | 2026-07-28 | Tue | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Blog #1 FINAL. Hand to aaradhya for publish. | Final file
8 | 2026-07-28 | Tue | W2 Prove | ishit | Marketing — Content | 3 | 13:00 | 16:00 | 3 | Blog #2 outline: MT5 Automation with Profytron. | Outline
8 | 2026-07-28 | Tue | W2 Prove | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Caption for publish day social. | Caption
8 | 2026-07-28 | Tue | W2 Prove | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup. | Done
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Join MetaAPI or payment UAT session fully. | Session attended
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Draft internal allowlist emails (team only). | Draft list
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Coach Insights admin click-through. | Notes on gaps
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Friday: 45m W2 review with whole team. | Review notes
9 | 2026-07-29 | Wed | W2 Prove | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD wrap. | Logged
9 | 2026-07-29 | Wed | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
9 | 2026-07-29 | Wed | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Live checkout UAT (Stripe or Razorpay). Complete test payment. | Payment succeeded | N | Live Payments UAT still open
9 | 2026-07-29 | Wed | W2 Prove | sunish | Eng — Infra/Trading | 3 | 14:00 | 17:00 | 3 | Verify webhook → plan entitlement in DB/UI. Screenshot before/after. | Entitlement proof | N | Live Payments UAT still open
9 | 2026-07-29 | Wed | W2 Prove | sunish | Eng — Infra/Trading | 4 | 17:00 | 18:00 | 1 | Note refund/cancel path for safety. | Note written
9 | 2026-07-29 | Wed | W2 Prove | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD evidence pack. | Saved
9 | 2026-07-29 | Wed | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
9 | 2026-07-29 | Wed | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Implement pricing copy from ishit. | Live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
9 | 2026-07-29 | Wed | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 16:00 | 3 | Billing UI polish (plan cards spacing/CTA). | PR merged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
9 | 2026-07-29 | Wed | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Help publish blog #1 layout if CMS/MDX needs tweak. | Blog renders | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
9 | 2026-07-29 | Wed | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | CRM → 100 TARGET HIT. Freeze quality bar. | 100
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Tag top 30 for future beta invites. | Top 30 tagged
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Share blog #1 in 3 relevant communities (value-first). | 3 shares
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Reply to all CRM responses same day. | Replies done
9 | 2026-07-29 | Wed | W2 Prove | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD celebrate 100 in chat (seriously). | Posted
9 | 2026-07-29 | Wed | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. Confirm blog #1 is live. Fix typos if any. | Live+typo pass
9 | 2026-07-29 | Wed | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 14:00 | 4 | Blog #2 draft. | Draft
9 | 2026-07-29 | Wed | W2 Prove | ishit | Marketing — Content | 3 | 14:00 | 16:00 | 2 | Social post announcing blog #1 — publish. | Posted
9 | 2026-07-29 | Wed | W2 Prove | ishit | Marketing — Content | 4 | 16:00 | 18:00 | 2 | Start blog #3 outline: AI Trading Coach. | Outline
9 | 2026-07-29 | Wed | W2 Prove | ishit | Marketing — Content | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: UAT order OTP→Pay→MetaAPI. | Order confirmed
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Witness live UAT; save screenshots into evidence folder. | Evidence files saved
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Unblock API keys / dashboard access for payments or MetaAPI. | Keys available
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Review published blog for factual errors before/after go-live. | Corrections sent
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Short sync with growth on Discord rules. | Rules agreed
10 | 2026-07-30 | Thu | W2 Prove | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD: mark UAT pass/fail in Track D style note. | Pass/fail logged
10 | 2026-07-30 | Thu | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup with MetaAPI account ready. | Creds ready | N | Get Bots / MetaAPI UAT still open
10 | 2026-07-30 | Thu | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 15:00 | 5 | Live MT5 connect UAT. Connect test account. Wait for sync. | Account connected | N | Get Bots / MetaAPI UAT still open
10 | 2026-07-30 | Thu | W2 Prove | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Confirm dashboard balance/positions updated. Screenshot. | Sync proof
10 | 2026-07-30 | Thu | W2 Prove | sunish | Eng — Infra/Trading | 4 | 16:00 | 17:00 | 1 | Log MetaAPI region/quota warnings. | Logged | N | Get Bots / MetaAPI UAT still open
10 | 2026-07-30 | Thu | W2 Prove | sunish | Eng — Infra/Trading | 5 | 17:00 | 18:00 | 1 | EOD. | Evidence saved
10 | 2026-07-30 | Thu | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
10 | 2026-07-30 | Thu | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Connected-accounts empty states clearer. | Merged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
10 | 2026-07-30 | Thu | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 16:00 | 3 | Safari/iOS login test on real device/browser. Log bugs. | Bug list | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
10 | 2026-07-30 | Thu | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Fix one auth cookie/redirect bug if found. | Fix or no-repro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
10 | 2026-07-30 | Thu | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Recruit 2 traders for MetaAPI test with sunish tomorrow/today. | 2 committed or pipeline
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Pin channel rules + intro message polished. | Pinned
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership shortlist: 10 brokers/creators with emails. | List of 10
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Engage blog commenters/DMs. | Engaged
10 | 2026-07-30 | Thu | W2 Prove | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
10 | 2026-07-30 | Thu | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
10 | 2026-07-30 | Thu | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 14:00 | 4 | Blog #2 revise + fact check with sunish on MT5 claims. | Revised
10 | 2026-07-30 | Thu | W2 Prove | ishit | Marketing — Content | 3 | 14:00 | 16:00 | 2 | Social post #2. | Posted
10 | 2026-07-30 | Thu | W2 Prove | ishit | Marketing — Content | 4 | 16:00 | 18:00 | 2 | Blog #3 outline expand to section bullets. | Bullets
10 | 2026-07-30 | Thu | W2 Prove | ishit | Marketing — Content | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup. | Done
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Join MetaAPI or payment UAT session fully. | Session attended
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Draft internal allowlist emails (team only). | Draft list
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Coach Insights admin click-through. | Notes on gaps
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Friday: 45m W2 review with whole team. | Review notes
11 | 2026-07-31 | Fri | W2 Prove | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD wrap. | Logged
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | AI Coach live stream with prod keys. Ask 5 real questions. | 5 answers captured
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 3 | 13:00 | 15:00 | 2 | Coach Insights migration/admin page confirm. | Admin loads
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Triage UAT leftover bugs into P0/P1. | Board updated
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | Help growth's test traders schedule if any. | Scheduled or N/A
11 | 2026-07-31 | Fri | W2 Prove | sunish | Eng — Infra/Trading | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Alpha Coach empty states + loading UX. | Merged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Help center information architecture for FAQs. | IA sketch | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Lighthouse remeasure after SEO/LCP work. | New score saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Support sunish UI needs for UAT screenshots. | Helped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
11 | 2026-07-31 | Fri | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
11 | 2026-07-31 | Fri | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send partnership emails #1–3 (personalized). | 3 sent
11 | 2026-07-31 | Fri | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 16:00 | 3 | Follow-ups on trader recruits; sit in UAT if useful (notes only). | Notes
11 | 2026-07-31 | Fri | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | CRM hygiene + reply queue zero. | Queue zero
11 | 2026-07-31 | Fri | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
11 | 2026-07-31 | Fri | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
11 | 2026-07-31 | Fri | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Blog #3 draft. | Draft
11 | 2026-07-31 | Fri | W2 Prove | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Social post #3. | Posted
11 | 2026-07-31 | Fri | W2 Prove | ishit | Marketing — Content | 4 | 14:00 | 17:00 | 3 | FAQ answers batch: write 3 solid answers. | 3 FAQs
11 | 2026-07-31 | Fri | W2 Prove | ishit | Marketing — Content | 5 | 17:00 | 18:00 | 1 | EOD. | Logged
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: UAT order OTP→Pay→MetaAPI. | Order confirmed
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Witness live UAT; save screenshots into evidence folder. | Evidence files saved
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Unblock API keys / dashboard access for payments or MetaAPI. | Keys available
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Review published blog for factual errors before/after go-live. | Corrections sent
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Short sync with growth on Discord rules. | Rules agreed
12 | 2026-08-01 | Sat | W2 Prove | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD: mark UAT pass/fail in Track D style note. | Pass/fail logged
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Fix highest P0 from UAT week. | P0 closed or mitigated
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 3 | 13:00 | 15:00 | 2 | Trigger test alert (uptime/Sentry) and confirm notification. | Alert received
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Deploy window: ship safe fixes only. | Deploy done
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | W2 review with team. | Attended
12 | 2026-08-01 | Sat | W2 Prove | sunish | Eng — Infra/Trading | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
12 | 2026-08-01 | Sat | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
12 | 2026-08-01 | Sat | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Ship remaining SEO fixes. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
12 | 2026-08-01 | Sat | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 16:00 | 3 | Final Lighthouse mobile home run. Compare to Day 2. | Comparison posted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
12 | 2026-08-01 | Sat | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | W2 review attend + take UI notes. | Notes | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
12 | 2026-08-01 | Sat | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup / W2 review. | Attended
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Partnership emails #4–6. | 3 sent
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Invite ~10 soft members to Discord (interested prospects). | Invites sent
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | First micro growth report: CRM size, replies, channel size. | Report posted
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
12 | 2026-08-01 | Sat | W2 Prove | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | Schedule next week invite shortlist brainstorm. | Scheduled
12 | 2026-08-01 | Sat | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | W2 review. | Attended
12 | 2026-08-01 | Sat | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish blog #2 (with aaradhya). | Live
12 | 2026-08-01 | Sat | W2 Prove | ishit | Marketing — Content | 3 | 13:00 | 16:00 | 3 | FAQ answers batch: +3 (total 6). | 6 FAQs
12 | 2026-08-01 | Sat | W2 Prove | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Social post #4. | Posted
12 | 2026-08-01 | Sat | W2 Prove | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
13 | 2026-08-02 | Sun | W2 Prove | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
13 | 2026-08-02 | Sun | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
13 | 2026-08-02 | Sun | W2 Prove | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
13 | 2026-08-02 | Sun | W2 Prove | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
13 | 2026-08-02 | Sun | W2 Prove | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
13 | 2026-08-02 | Sun | W2 Prove | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
13 | 2026-08-02 | Sun | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
13 | 2026-08-02 | Sun | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
13 | 2026-08-02 | Sun | W2 Prove | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
13 | 2026-08-02 | Sun | W2 Prove | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
13 | 2026-08-02 | Sun | W2 Prove | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
13 | 2026-08-02 | Sun | W2 Prove | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
13 | 2026-08-02 | Sun | W2 Prove | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: UAT order OTP→Pay→MetaAPI. | Order confirmed
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Witness live UAT; save screenshots into evidence folder. | Evidence files saved
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | Unblock API keys / dashboard access for payments or MetaAPI. | Keys available
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Review published blog for factual errors before/after go-live. | Corrections sent
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Short sync with growth on Discord rules. | Rules agreed
14 | 2026-08-03 | Mon | W2 Prove | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD: mark UAT pass/fail in Track D style note. | Pass/fail logged
14 | 2026-08-03 | Mon | W2 Prove | sunish | Eng — Infra/Trading | 1 | 9:00 | 11:00 | 2 | Wallet smoke OR rate-limit smoke (pick based on risk). | Test result
14 | 2026-08-03 | Mon | W2 Prove | sunish | Eng — Infra/Trading | 2 | 11:00 | 14:00 | 3 | Chip away P1 UAT bugs. | ≥1 P1 closed
14 | 2026-08-03 | Mon | W2 Prove | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Document evidence index README for Track D folder. | README exists
14 | 2026-08-03 | Mon | W2 Prove | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Rest brain: no big refactors. | No refactor
14 | 2026-08-03 | Mon | W2 Prove | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD light. | Logged
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Funnel watch. | Noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Hotfix onboarding/UX only. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Final polish CTAs for new invites. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Write web/UX retro bullets. | Retro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV final snapshot. | Saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
14 | 2026-08-03 | Mon | W2 Prove | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
14 | 2026-08-03 | Mon | W2 Prove | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 14:00 | 4 | Invite waves toward 100. Track every send. | Sends logged
14 | 2026-08-03 | Mon | W2 Prove | abhishek kushwaha | Marketing — Growth | 3 | 14:00 | 16:00 | 2 | Partnership announce if ready; else more invites. | Action taken
14 | 2026-08-03 | Mon | W2 Prove | abhishek kushwaha | Marketing — Growth | 4 | 16:00 | 18:00 | 2 | Growth retro: what channel worked. | Retro bullets
14 | 2026-08-03 | Mon | W2 Prove | abhishek kushwaha | Marketing — Growth | 5 | 18:00 | 19:00 | 1 | EOD user/invite counts. | Logged
14 | 2026-08-03 | Mon | W2 Prove | ishit | Marketing — Content | 1 | 9:00 | 12:00 | 3 | Blog #3 revise/publish path. | Ready or live
14 | 2026-08-03 | Mon | W2 Prove | ishit | Marketing — Content | 2 | 12:00 | 14:00 | 2 | FAQ +3 (toward 10). | FAQs progressing
14 | 2026-08-03 | Mon | W2 Prove | ishit | Marketing — Content | 3 | 14:00 | 16:00 | 2 | Social posts written for queue. | Queued
14 | 2026-08-03 | Mon | W2 Prove | ishit | Marketing — Content | 4 | 16:00 | 18:00 | 2 | Rest/edit pass — cut hype language. | Cleaner copy
14 | 2026-08-03 | Mon | W2 Prove | ishit | Marketing — Content | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
15 | 2026-08-04 | Tue | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
15 | 2026-08-04 | Tue | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
15 | 2026-08-04 | Tue | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
15 | 2026-08-04 | Tue | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
15 | 2026-08-04 | Tue | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
15 | 2026-08-04 | Tue | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
15 | 2026-08-04 | Tue | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
16 | 2026-08-05 | Wed | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
16 | 2026-08-05 | Wed | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
16 | 2026-08-05 | Wed | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
16 | 2026-08-05 | Wed | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
16 | 2026-08-05 | Wed | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
16 | 2026-08-05 | Wed | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
16 | 2026-08-05 | Wed | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
17 | 2026-08-06 | Thu | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
17 | 2026-08-06 | Thu | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
17 | 2026-08-06 | Thu | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
17 | 2026-08-06 | Thu | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
17 | 2026-08-06 | Thu | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
17 | 2026-08-06 | Thu | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
17 | 2026-08-06 | Thu | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
18 | 2026-08-07 | Fri | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
18 | 2026-08-07 | Fri | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
18 | 2026-08-07 | Fri | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
18 | 2026-08-07 | Fri | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
18 | 2026-08-07 | Fri | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
18 | 2026-08-07 | Fri | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
18 | 2026-08-07 | Fri | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
19 | 2026-08-08 | Sat | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
19 | 2026-08-08 | Sat | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
19 | 2026-08-08 | Sat | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
19 | 2026-08-08 | Sat | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
19 | 2026-08-08 | Sat | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
19 | 2026-08-08 | Sat | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
19 | 2026-08-08 | Sat | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
20 | 2026-08-09 | Sun | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
20 | 2026-08-09 | Sun | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
20 | 2026-08-09 | Sun | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
20 | 2026-08-09 | Sun | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
20 | 2026-08-09 | Sun | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
20 | 2026-08-09 | Sun | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
20 | 2026-08-09 | Sun | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
20 | 2026-08-09 | Sun | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
20 | 2026-08-09 | Sun | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
20 | 2026-08-09 | Sun | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
20 | 2026-08-09 | Sun | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
20 | 2026-08-09 | Sun | W3 Dogfood | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + dogfood user check-ins. | Heard from ≥2 dogfood users
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Triage feedback into P0/P1/P2 list with eng. | Prioritized board
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Allowlist / legal / restore-drill decisions as needed today. | Decision or progress note
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Approve invite email + welcome sequence copy. | Approved
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Personalize or review the 20-invite shortlist with growth. | List locked
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: GO/NO-GO pulse for beta week. | Pulse written
21 | 2026-08-10 | Mon | W3 Dogfood | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup / dogfood channel watch. | Seen overnight issues
21 | 2026-08-10 | Mon | W3 Dogfood | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix P0 from dogfood (sync/auth/payment). | P0 fixed or ETA
21 | 2026-08-10 | Mon | W3 Dogfood | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Paper trading path check for safe onboarding. | Path works or bug filed
21 | 2026-08-10 | Mon | W3 Dogfood | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Allowlist env verify when abhishek sets emails. | Verified or waiting
21 | 2026-08-10 | Mon | W3 Dogfood | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD bug counts. | Counts posted
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup / dogfood UI bugs. | List refreshed | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Onboarding + risk page UX polish. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Implement FAQ content ishit finished. | FAQs live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Community page Discord links live. | Links work | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | P0 UI from dogfood. | Fixed or queued | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Build / confirm 20 beta invite names from top 30 + backups 10. | Lists ready
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Personalize invite notes (not mail merge garbage). | 20 notes
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partnership touches #7–10 or follow-ups. | Touches
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Community daily: answer 5 messages. | 5 answers
21 | 2026-08-10 | Mon | W3 Dogfood | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD list to abhishek for approve. | Sent for approve
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Beta invite email + welcome email #1 copy. | Copy ready
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Welcome emails #2–3 drafts. | Drafts
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | MT5 connect guide draft sections. | Guide progressing
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | FAQ push toward 10–15. | Count up
21 | 2026-08-10 | Mon | W3 Dogfood | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD send copies for approval. | Sent
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
22 | 2026-08-11 | Tue | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
22 | 2026-08-11 | Tue | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
22 | 2026-08-11 | Tue | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
22 | 2026-08-11 | Tue | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
22 | 2026-08-11 | Tue | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Today we send. | Ready
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send 20 beta invites (email/DM as planned). Track delivery. | 20 sent
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Welcome each accepter in Discord by name. | Welcomes done
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | DM non-openers once (same day evening). | Nudges sent
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Log yes/no/maybe counts. | Counts
22 | 2026-08-11 | Tue | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD report to abhishek. | Reported
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
22 | 2026-08-11 | Tue | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
23 | 2026-08-12 | Wed | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
23 | 2026-08-12 | Wed | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
23 | 2026-08-12 | Wed | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
23 | 2026-08-12 | Wed | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
23 | 2026-08-12 | Wed | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Help 5 users activate (broker connect handholding). | 5 helped
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Log objections in a plain doc. | Objections doc
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Community moderation + energy. | Channel healthy
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Optional: 5 more waitlist yeses. | Progress
23 | 2026-08-12 | Wed | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD activation assist count. | Logged
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
23 | 2026-08-12 | Wed | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
24 | 2026-08-13 | Thu | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
24 | 2026-08-13 | Thu | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
24 | 2026-08-13 | Thu | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
24 | 2026-08-13 | Thu | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
24 | 2026-08-13 | Thu | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Help 5 users activate (broker connect handholding). | 5 helped
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Log objections in a plain doc. | Objections doc
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Community moderation + energy. | Channel healthy
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Optional: 5 more waitlist yeses. | Progress
24 | 2026-08-13 | Thu | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD activation assist count. | Logged
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
24 | 2026-08-13 | Thu | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
25 | 2026-08-14 | Fri | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
25 | 2026-08-14 | Fri | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
25 | 2026-08-14 | Fri | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
25 | 2026-08-14 | Fri | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
25 | 2026-08-14 | Fri | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Help 5 users activate (broker connect handholding). | 5 helped
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Log objections in a plain doc. | Objections doc
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Community moderation + energy. | Channel healthy
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Optional: 5 more waitlist yeses. | Progress
25 | 2026-08-14 | Fri | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD activation assist count. | Logged
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
25 | 2026-08-14 | Fri | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
26 | 2026-08-15 | Sat | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
26 | 2026-08-15 | Sat | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
26 | 2026-08-15 | Sat | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
26 | 2026-08-15 | Sat | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
26 | 2026-08-15 | Sat | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Help 5 users activate (broker connect handholding). | 5 helped
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Log objections in a plain doc. | Objections doc
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Community moderation + energy. | Channel healthy
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Optional: 5 more waitlist yeses. | Progress
26 | 2026-08-15 | Sat | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD activation assist count. | Logged
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
26 | 2026-08-15 | Sat | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
27 | 2026-08-16 | Sun | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
27 | 2026-08-16 | Sun | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
27 | 2026-08-16 | Sun | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
27 | 2026-08-16 | Sun | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
27 | 2026-08-16 | Sun | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
27 | 2026-08-16 | Sun | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
27 | 2026-08-16 | Sun | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
27 | 2026-08-16 | Sun | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
27 | 2026-08-16 | Sun | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
27 | 2026-08-16 | Sun | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
27 | 2026-08-16 | Sun | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
27 | 2026-08-16 | Sun | W4 Beta20 | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Morning: check invite opens/signups. Reply to stuck users yourself. | Stuck users unblocked or listed
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Support hour in Discord/Telegram. | Questions answered
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Do 1–2 user calls (15m) if scheduled. | Call notes
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Prioritize hotfixes with eng from real user pain. | Top 3 fixes ordered
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Metrics: activation count, SEV1 count. | Numbers in KPI tab
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD: thank the team; note tomorrow's risk. | Note done
28 | 2026-08-17 | Mon | W4 Beta20 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | On-call morning sweep of Sentry + Discord. | Sweep done
28 | 2026-08-17 | Mon | W4 Beta20 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfix beta blockers (OTP, broker connect, balances). | Hotfix shipped or workaround
28 | 2026-08-17 | Mon | W4 Beta20 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Reproduce 1 user-reported MetaAPI issue. | Repro steps
28 | 2026-08-17 | Mon | W4 Beta20 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Keep staging/prod parity notes. | Notes updated
28 | 2026-08-17 | Mon | W4 Beta20 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD handoff note for night. | Handoff written
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Watch PostHog funnel drop-offs morning. | Drop step named | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix onboarding/registration UX causing drop-offs. | Fix shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Hotfix UI for beta confusion. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Ship FAQ updates from beta questions. | Updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | EOD funnel note. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | Quick regression on mobile signup. | Still works | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Help 5 users activate (broker connect handholding). | 5 helped
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Log objections in a plain doc. | Objections doc
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Community moderation + energy. | Channel healthy
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Optional: 5 more waitlist yeses. | Progress
28 | 2026-08-17 | Mon | W4 Beta20 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD activation assist count. | Logged
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 2 | 10:00 | 12:00 | 2 | Community-only welcome post (not public hype). | Posted in community
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 3 | 12:00 | 15:00 | 3 | Turn beta questions into 2 public FAQs. | FAQs live
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short/Reel script #1 + record if possible. | Script or recording
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social educational post. | Posted
28 | 2026-08-17 | Mon | W4 Beta20 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
29 | 2026-08-18 | Tue | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
29 | 2026-08-18 | Tue | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
29 | 2026-08-18 | Tue | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
29 | 2026-08-18 | Tue | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
29 | 2026-08-18 | Tue | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
29 | 2026-08-18 | Tue | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
29 | 2026-08-18 | Tue | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
30 | 2026-08-19 | Wed | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
30 | 2026-08-19 | Wed | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
30 | 2026-08-19 | Wed | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
30 | 2026-08-19 | Wed | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
30 | 2026-08-19 | Wed | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
30 | 2026-08-19 | Wed | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
30 | 2026-08-19 | Wed | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
31 | 2026-08-20 | Thu | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
31 | 2026-08-20 | Thu | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
31 | 2026-08-20 | Thu | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
31 | 2026-08-20 | Thu | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
31 | 2026-08-20 | Thu | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
31 | 2026-08-20 | Thu | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
31 | 2026-08-20 | Thu | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
32 | 2026-08-21 | Fri | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
32 | 2026-08-21 | Fri | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
32 | 2026-08-21 | Fri | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
32 | 2026-08-21 | Fri | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
32 | 2026-08-21 | Fri | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
32 | 2026-08-21 | Fri | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
32 | 2026-08-21 | Fri | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
33 | 2026-08-22 | Sat | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
33 | 2026-08-22 | Sat | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
33 | 2026-08-22 | Sat | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
33 | 2026-08-22 | Sat | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
33 | 2026-08-22 | Sat | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
33 | 2026-08-22 | Sat | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
33 | 2026-08-22 | Sat | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
34 | 2026-08-23 | Sun | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
34 | 2026-08-23 | Sun | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
34 | 2026-08-23 | Sun | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
34 | 2026-08-23 | Sun | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
34 | 2026-08-23 | Sun | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
34 | 2026-08-23 | Sun | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
34 | 2026-08-23 | Sun | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
34 | 2026-08-23 | Sun | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
34 | 2026-08-23 | Sun | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
34 | 2026-08-23 | Sun | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
34 | 2026-08-23 | Sun | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
34 | 2026-08-23 | Sun | W5 Expand50 | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup + Coach Insights skim. | 1 insight → action
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Approve next invite wave size. | Number locked
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Partnership call or follow-up emails. | 2 touchpoints
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Product decisions from AMA/feedback. | 1 decision written
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Review case study draft for accuracy. | Redlines sent
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD KPI update. | KPI tab updated
35 | 2026-08-24 | Mon | W5 Expand50 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
35 | 2026-08-24 | Mon | W5 Expand50 | sunish | Eng — Infra/Trading | 2 | 10:00 | 13:00 | 3 | Copy-trading or bots UAT leftover for power users. | Progress logged
35 | 2026-08-24 | Mon | W5 Expand50 | sunish | Eng — Infra/Trading | 3 | 13:00 | 16:00 | 3 | Fix slow API endpoint found in beta usage. | Latency improved or profiled
35 | 2026-08-24 | Mon | W5 Expand50 | sunish | Eng — Infra/Trading | 4 | 14:00 | 16:00 | 2 | Coach thumbs-down intents quick wins. | 1 intent improved
35 | 2026-08-24 | Mon | W5 Expand50 | sunish | Eng — Infra/Trading | 5 | 16:00 | 17:00 | 1 | EOD. | Logged
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Standup. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Add/verify time-to-first-broker PostHog events. | Events firing | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Dashboard polish from AMA feedback. | PR | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Internal linking between blog/guides/pricing. | Links live | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV spot check. | Numbers | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Send next invite wave (batch toward 50). | Batch sent
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Win-back inactive beta users (personal DMs). | DMs sent
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Partner follow-ups / AMA promo in community. | Promo done
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Weekly growth report numbers. | Report
35 | 2026-08-24 | Mon | W5 Expand50 | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Risk management guide write/publish. | Guide progress/live
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Case study draft from real user (with consent). | Draft
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Short #2 script/record. | Progress
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Social #7–8. | Posted
35 | 2026-08-24 | Mon | W5 Expand50 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
36 | 2026-08-25 | Tue | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
36 | 2026-08-25 | Tue | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Confirm feature freeze with team. | Freeze on
36 | 2026-08-25 | Tue | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 15:00 | 5 | Run pnpm load:d7:100 against healthy API. Save summary. | Report file
36 | 2026-08-25 | Tue | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Classify failures (timeouts vs 5xx vs app). | Classification table
36 | 2026-08-25 | Tue | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 17:00 | 1 | Share report with abhishek. | Shared
36 | 2026-08-25 | Tue | W6 Harden | sunish | Eng — Infra/Trading | 5 | 17:00 | 18:00 | 1 | EOD no new features. | Respected freeze
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
36 | 2026-08-25 | Tue | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
36 | 2026-08-25 | Tue | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
37 | 2026-08-26 | Wed | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
37 | 2026-08-26 | Wed | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
37 | 2026-08-26 | Wed | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix load/security item from gap list. | Item closed
37 | 2026-08-26 | Wed | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Security Playwright or secret rotation step. | Step done
37 | 2026-08-26 | Wed | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Update runbook with exact commands that worked. | Runbook updated
37 | 2026-08-26 | Wed | W6 Harden | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
37 | 2026-08-26 | Wed | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
37 | 2026-08-26 | Wed | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
38 | 2026-08-27 | Thu | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
38 | 2026-08-27 | Thu | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
38 | 2026-08-27 | Thu | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix load/security item from gap list. | Item closed
38 | 2026-08-27 | Thu | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Security Playwright or secret rotation step. | Step done
38 | 2026-08-27 | Thu | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Update runbook with exact commands that worked. | Runbook updated
38 | 2026-08-27 | Thu | W6 Harden | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
38 | 2026-08-27 | Thu | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
38 | 2026-08-27 | Thu | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
39 | 2026-08-28 | Fri | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
39 | 2026-08-28 | Fri | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
39 | 2026-08-28 | Fri | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix load/security item from gap list. | Item closed
39 | 2026-08-28 | Fri | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Security Playwright or secret rotation step. | Step done
39 | 2026-08-28 | Fri | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Update runbook with exact commands that worked. | Runbook updated
39 | 2026-08-28 | Fri | W6 Harden | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
39 | 2026-08-28 | Fri | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
39 | 2026-08-28 | Fri | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
40 | 2026-08-29 | Sat | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
40 | 2026-08-29 | Sat | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
40 | 2026-08-29 | Sat | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix load/security item from gap list. | Item closed
40 | 2026-08-29 | Sat | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Security Playwright or secret rotation step. | Step done
40 | 2026-08-29 | Sat | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Update runbook with exact commands that worked. | Runbook updated
40 | 2026-08-29 | Sat | W6 Harden | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
40 | 2026-08-29 | Sat | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
40 | 2026-08-29 | Sat | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Skim overnight Slack/Discord/email. Reply only to blockers. | Inbox zero for red items
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 11:00 | 1 | Update Executive Dashboard numbers from Master Tracker. | Dashboard counts match reality
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 3 | 11:00 | 12:00 | 1 | Write 5 bullets: what slipped yesterday, what must not slip tomorrow. | Note in Weekly Review tab
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 4 | 12:00 | 13:00 | 1 | Quick call or voice note to sunish OR aaradhya if anything is on fire. | Fire acknowledged or N/A
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 5 | 13:00 | 14:00 | 1 | Personal admin + rest buffer (still count as wrap). | Phone on DND after
41 | 2026-08-30 | Sun | W6 Harden | abhishek | All-Rounder | 6 | 14:00 | 15:00 | 1 | Light: skim 1 competitor site or 1 user message thread. | 1 insight written
41 | 2026-08-30 | Sun | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Check uptime / Sentry / error spikes. No heroics unless SEV1. | Status green or ticket filed
41 | 2026-08-30 | Sun | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 12:00 | 2 | Clear one leftover chore from the week (script, doc, tiny fix). | Chore closed
41 | 2026-08-30 | Sun | W6 Harden | sunish | Eng — Infra/Trading | 3 | 12:00 | 13:00 | 1 | Update Deployment Tracker row with real URLs/versions. | Tracker honest
41 | 2026-08-30 | Sun | W6 Harden | sunish | Eng — Infra/Trading | 4 | 13:00 | 14:00 | 1 | Prep Monday's first command list in a notepad. | Monday plan written
41 | 2026-08-30 | Sun | W6 Harden | sunish | Eng — Infra/Trading | 5 | 14:00 | 15:00 | 1 | Rest eyes. Light reading of MetaAPI/GCP quota only if needed. | Done
41 | 2026-08-30 | Sun | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Check Vercel/web deploy + /status manually. | Page loads or bug noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
41 | 2026-08-30 | Sun | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 12:00 | 2 | One small UI chore (typo, spacing, mobile overflow). | PR or fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
41 | 2026-08-30 | Sun | W6 Harden | aaradhya | Eng — Frontend | 3 | 12:00 | 13:00 | 1 | Update Website Checklist tab honestly. | Checklist updated | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
41 | 2026-08-30 | Sun | W6 Harden | aaradhya | Eng — Frontend | 4 | 13:00 | 14:00 | 1 | Prep Monday Lighthouse run command. | Command ready | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
41 | 2026-08-30 | Sun | W6 Harden | aaradhya | Eng — Frontend | 5 | 14:00 | 15:00 | 1 | Rest. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Reply only to warm leads. No cold blasting on Sunday. | Replies sent
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 11:00 | 1 | Clean CRM: remove junk rows, fix statuses. | CRM cleaner
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 11:00 | 12:00 | 1 | Skim competitor social for 20 min. Note 3 ideas. | 3 ideas
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 12:00 | 13:00 | 1 | Plan Monday outreach list (10 names). | List ready
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 13:00 | 14:00 | 1 | Rest. | Done
41 | 2026-08-30 | Sun | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 14:00 | 15:00 | 1 | Optional: engage in 1 community thread helpfully (no spam). | 1 helpful comment
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Light edit only — no new long drafts if burned. | Small edit or rest
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 11:00 | 1 | Schedule or queue 1 social post for Monday. | Queued
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 3 | 11:00 | 12:00 | 1 | Collect screenshots/assets folder tidy. | Folder tidy
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 4 | 12:00 | 13:00 | 1 | Read one published post out loud. Fix awkward lines. | Fixes
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 5 | 13:00 | 14:00 | 1 | Rest. | Done
41 | 2026-08-30 | Sun | W6 Harden | ishit | Marketing — Content | 6 | 14:00 | 15:00 | 1 | Optional: reply to comments on posts. | Replies
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Standup: feature freeze rules remind. | Freeze understood
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 2 | 10:00 | 13:00 | 3 | Review load-test or security results with sunish. | Gap list owned
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 3 | 13:00 | 15:00 | 2 | GO/NO-GO notes toward 100 users. | Written draft
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Runbook gaps closed (you write plain English). | Runbook section updated
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 5 | 16:00 | 17:00 | 1 | Quiet check-in with growth (no big campaigns). | Aligned
42 | 2026-08-31 | Mon | W6 Harden | abhishek | All-Rounder | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
42 | 2026-08-31 | Mon | W6 Harden | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Standup. | Done
42 | 2026-08-31 | Mon | W6 Harden | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Fix load/security item from gap list. | Item closed
42 | 2026-08-31 | Mon | W6 Harden | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Security Playwright or secret rotation step. | Step done
42 | 2026-08-31 | Mon | W6 Harden | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Update runbook with exact commands that worked. | Runbook updated
42 | 2026-08-31 | Mon | W6 Harden | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD. | Logged
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Feature freeze: bugs only. | No features | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Fix frontend errors seen under load / Sentry. | Fix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Reduce noisy refetch/polling if identified. | Change or N/A | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Status page trust polish. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | Image alt / OG leftovers. | Done | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. Quiet growth week. | Understood
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 13:00 | 3 | Nurture only: reply, help, no big blasts. | Nurture log
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 3 | 13:00 | 15:00 | 2 | Prep segmented list for scale-to-100 week. | Segments ready
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 4 | 14:00 | 16:00 | 2 | Referral soft ask to activated users. | Asks sent
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 5 | 16:00 | 17:00 | 1 | Pipeline doc update. | Updated
42 | 2026-08-31 | Mon | W6 Harden | abhishek kushwaha | Marketing — Growth | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Quiet content week — no hype launches. | Respected
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Publish case study / trust content. | Published
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Internal links suggestions for aaradhya. | List
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Educational posts only (2). | Posted
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Prep scale-week content burst outlines. | Outlines
42 | 2026-08-31 | Mon | W6 Harden | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Activation standup 15m. | Blockers listed
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Unblock users stuck on broker/OTP personally. | Helped ≥3 people
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Watch capacity with eng; approve hotfixes only. | No feature creep
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Decide messaging for scale invites with growth. | Copy approved
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Start retro bullets (eng/marketing/product). | Retro started
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD user count snapshot. | Number logged
43 | 2026-09-01 | Tue | W7 Scale100 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Watch Cloud Run metrics / errors. | No silent fire
43 | 2026-09-01 | Tue | W7 Scale100 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfixes only for scale week. | Hotfix or idle with monitoring
43 | 2026-09-01 | Tue | W7 Scale100 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Quota checks MetaAPI / DB connections. | Quotas OK or raised
43 | 2026-09-01 | Tue | W7 Scale100 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Write eng retro bullets. | Retro bullets
43 | 2026-09-01 | Tue | W7 Scale100 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD user-load note. | Logged
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Funnel watch. | Noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Hotfix onboarding/UX only. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Final polish CTAs for new invites. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Write web/UX retro bullets. | Retro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV final snapshot. | Saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 14:00 | 4 | Invite waves toward 100. Track every send. | Sends logged
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 3 | 14:00 | 16:00 | 2 | Partnership announce if ready; else more invites. | Action taken
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 4 | 16:00 | 18:00 | 2 | Growth retro: what channel worked. | Retro bullets
43 | 2026-09-01 | Tue | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 5 | 18:00 | 19:00 | 1 | EOD user/invite counts. | Logged
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Content burst: remix blog + 3 socials. | Shipped
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Short #3. | Done or scheduled
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Content retro: what performed. | Retro
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Next 30d editorial calendar skeleton. | Calendar
43 | 2026-09-01 | Tue | W7 Scale100 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Activation standup 15m. | Blockers listed
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Unblock users stuck on broker/OTP personally. | Helped ≥3 people
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Watch capacity with eng; approve hotfixes only. | No feature creep
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Decide messaging for scale invites with growth. | Copy approved
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Start retro bullets (eng/marketing/product). | Retro started
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD user count snapshot. | Number logged
44 | 2026-09-02 | Wed | W7 Scale100 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Watch Cloud Run metrics / errors. | No silent fire
44 | 2026-09-02 | Wed | W7 Scale100 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfixes only for scale week. | Hotfix or idle with monitoring
44 | 2026-09-02 | Wed | W7 Scale100 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Quota checks MetaAPI / DB connections. | Quotas OK or raised
44 | 2026-09-02 | Wed | W7 Scale100 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Write eng retro bullets. | Retro bullets
44 | 2026-09-02 | Wed | W7 Scale100 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD user-load note. | Logged
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Funnel watch. | Noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Hotfix onboarding/UX only. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Final polish CTAs for new invites. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Write web/UX retro bullets. | Retro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV final snapshot. | Saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 14:00 | 4 | Invite waves toward 100. Track every send. | Sends logged
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 3 | 14:00 | 16:00 | 2 | Partnership announce if ready; else more invites. | Action taken
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 4 | 16:00 | 18:00 | 2 | Growth retro: what channel worked. | Retro bullets
44 | 2026-09-02 | Wed | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 5 | 18:00 | 19:00 | 1 | EOD user/invite counts. | Logged
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Content burst: remix blog + 3 socials. | Shipped
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Short #3. | Done or scheduled
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Content retro: what performed. | Retro
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Next 30d editorial calendar skeleton. | Calendar
44 | 2026-09-02 | Wed | W7 Scale100 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 1 | 9:00 | 10:00 | 1 | Activation standup 15m. | Blockers listed
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 2 | 10:00 | 12:00 | 2 | Unblock users stuck on broker/OTP personally. | Helped ≥3 people
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 3 | 12:00 | 14:00 | 2 | Watch capacity with eng; approve hotfixes only. | No feature creep
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 4 | 14:00 | 16:00 | 2 | Decide messaging for scale invites with growth. | Copy approved
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 5 | 16:00 | 18:00 | 2 | Start retro bullets (eng/marketing/product). | Retro started
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek | All-Rounder | 6 | 18:00 | 19:00 | 1 | EOD user count snapshot. | Number logged
45 | 2026-09-03 | Thu | W7 Scale100 | sunish | Eng — Infra/Trading | 1 | 9:00 | 10:00 | 1 | Watch Cloud Run metrics / errors. | No silent fire
45 | 2026-09-03 | Thu | W7 Scale100 | sunish | Eng — Infra/Trading | 2 | 10:00 | 14:00 | 4 | Hotfixes only for scale week. | Hotfix or idle with monitoring
45 | 2026-09-03 | Thu | W7 Scale100 | sunish | Eng — Infra/Trading | 3 | 14:00 | 16:00 | 2 | Quota checks MetaAPI / DB connections. | Quotas OK or raised
45 | 2026-09-03 | Thu | W7 Scale100 | sunish | Eng — Infra/Trading | 4 | 16:00 | 18:00 | 2 | Write eng retro bullets. | Retro bullets
45 | 2026-09-03 | Thu | W7 Scale100 | sunish | Eng — Infra/Trading | 5 | 18:00 | 19:00 | 1 | EOD user-load note. | Logged
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 1 | 9:00 | 10:00 | 1 | Funnel watch. | Noted | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 2 | 10:00 | 13:00 | 3 | Hotfix onboarding/UX only. | Hotfix | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 3 | 13:00 | 15:00 | 2 | Final polish CTAs for new invites. | Shipped | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 4 | 14:00 | 16:00 | 2 | Write web/UX retro bullets. | Retro | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 5 | 16:00 | 17:00 | 1 | CWV final snapshot. | Saved | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | aaradhya | Eng — Frontend | 6 | 17:00 | 18:00 | 1 | EOD. | Logged | Y | FE eng complete package 2026-08-02; prod web-00074-nkc
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 1 | 9:00 | 10:00 | 1 | Standup. | Done
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 2 | 10:00 | 14:00 | 4 | Invite waves toward 100. Track every send. | Sends logged
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 3 | 14:00 | 16:00 | 2 | Partnership announce if ready; else more invites. | Action taken
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 4 | 16:00 | 18:00 | 2 | Growth retro: what channel worked. | Retro bullets
45 | 2026-09-03 | Thu | W7 Scale100 | abhishek kushwaha | Marketing — Growth | 5 | 18:00 | 19:00 | 1 | EOD user/invite counts. | Logged
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 1 | 9:00 | 10:00 | 1 | Standup. | Done
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 2 | 10:00 | 13:00 | 3 | Content burst: remix blog + 3 socials. | Shipped
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 3 | 13:00 | 15:00 | 2 | Short #3. | Done or scheduled
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 4 | 14:00 | 16:00 | 2 | Content retro: what performed. | Retro
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 5 | 16:00 | 17:00 | 1 | Next 30d editorial calendar skeleton. | Calendar
45 | 2026-09-03 | Thu | W7 Scale100 | ishit | Marketing — Content | 6 | 17:00 | 18:00 | 1 | EOD. | Logged

## Day by Day 1-45
Day | Date | Weekday | Phase | Daily Focus | abhishek (All-Rounder) | sunish (Eng Infra/Trading) | aaradhya (Eng Frontend) | abhishek kushwaha (Growth) | ishit (Content) | End-of-Day Deliverable | Status
1 | 2026-07-21 | Tue | W1 — Stabilize (M0) | Launch OS kickoff + marketing zero baseline | Kickoff: lock Day1–45 plan, approve GCP as primary host, share access (GSC/PostHog/Discord later) | Inventory prod: health probes, Cloud Run services, env secrets checklist | Audit landing LCP causes; list heavy 3D/motion to lazy-load; check /status route locally ¦ FE DONE 2026-08-02 (repo+prod deploy) | START FROM ZERO: create acquisition tracker sheet; define ICP (trader personas); list 20 communities to join | START FROM ZERO: brand voice 1-pager; collect product facts/screenshots needed; competitor homepage swipe file | Prod inventory reports 2026-07-21/22; team kickoff path started | Completed
2 | 2026-07-22 | Wed | W1 — Stabilize (M0) | API path chosen; LCP work started; marketing foundations | Decide Render decommission date; review sunish deploy plan; set SEV1 owner = you | Deploy/fix API on GCP Cloud Run (min-instances=1); document URLs | Start LCP PR: dynamic import hero visuals; defer non-critical JS ¦ FE DONE 2026-08-02 (repo+prod deploy) | Join 5 trader communities (read-only); start prospect CRM columns (name, channel, status) | Outline homepage hero angles (3 options); draft positioning bullets for growth | GCP API path + startupProbe /ready harden (PRODUCTION_STATUS) | Completed
3 | 2026-07-23 | Thu | W1 — Stabilize (M0) | M0 progress + first marketing assets | Verify /health with sunish; unblock secrets if missing | Fix API health until /live /ready /health = 200 for hours; enable basic uptime ping | Continue LCP; measure mobile Lighthouse before/after ¦ FE DONE 2026-08-02 (repo+prod deploy) | Build prospect list to 25 (LinkedIn/Twitter/Telegram leads) | Draft homepage H1 + subhead + CTA (v1); send to abhishek for approve | API /live /ready /health 200; uptime check created 2026-07-23 | Completed
4 | 2026-07-24 | Fri | W1 — Stabilize (M0) | Infra hardening + copy implementation | Approve homepage copy v1; review aaradhya LCP PR | Cloud SQL backups ON; remove/disable duplicate DB instance; rotate critical secrets plan | Implement approved hero copy in code; ship /status page to staging/prod ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 40; start competitor teardown notes (pricing, CTAs, claims) | Draft pricing page messaging; start blog outline #1 What is Copy Trading | Unused Cloud SQL stopped; prod backups ON; secret rotation PLAN only | Completed
5 | 2026-07-25 | Sat | W1 — Stabilize (M0) | Monitoring + content engine start | Wire Search Console property (or grant access); weekly goals check-in 30m | Wire Sentry DSN (API); confirm EXPOSE_DEV_OTP=false; SPF/DKIM checklist start | Wire Sentry web DSN; PostHog provider check; meta/title audit list for public pages ¦ FE DONE 2026-08-02 (repo+prod deploy) | w1` |  | Sentry API verified; EXPOSE_DEV_OTP OFF; email DNS -> Day 6 verified | Completed
6 | 2026-07-26 | Sun | W1 — Stabilize (M0) | Weekend push: email + content | Saturday review: blockers log; approve blog #1 direction | Email domain DNS (SPF/DKIM/DMARC) with Resend; test OTP email to yourself | Mobile QA pass on home/pricing/login; fix obvious layout bugs ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 70; competitor teardown doc finished | Revise blog #1; draft LinkedIn post #1 from blog; pricing copy v1 | Resend domain verified; OTP email delivered (Day 6). Marketing — no evidence | Completed
7 | 2026-07-27 | Mon | W1 — Stabilize (M0) | W1 close | Sunday light: update Executive Dashboard; plan Week 2 UAT order | Rest / on-call only OR finish health if still red | Rest / merge LCP PR if ready ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 80; rest of day light research | Rest / polish social calendar to 8 posts planned | W1 infra mostly green. Marketing >0 assets — NO evidence | Partial — aaradhya FE eng complete 2026-08-02
8 | 2026-07-28 | Tue | W2 — Prove live (M1–M4) | UAT day 1 + first publish prep | Declare UAT week; order: OTP → Payments → MetaAPI; assign evidence folder | Live OTP UAT formal (ALLOW_LIVE_EMAIL_OTP); file evidence | SEO code: robots/sitemap verify on prod; fix broken meta tags ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 90; Discord/Telegram channel CREATE (empty ok) | Blog #1 FINAL for publish; start blog #2 MT5 Automation outline | Formal live OTP UAT PASS (D7_OTP_UAT_20260728). Payment audit Day 8 (no live checkout). | Completed
9 | 2026-07-29 | Wed | W2 — Prove live (M1–M4) | Payments UAT + first SEO content live | Review OTP evidence; unblock payment keys if needed | Live payment UAT (Stripe OR Razorpay) + webhook entitlement proof | Implement pricing page copy; billing UI polish from growth notes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect list → 100 (TARGET); tag top 30 for beta invite later | Publish blog #1 live; draft blog #2 | Trial RC + Medium fixes (local). Live Payments UAT OPEN. Blog publish — NO evidence. | Partial — aaradhya FE eng complete 2026-08-02
10 | 2026-07-30 | Thu | W2 — Prove live (M1–M4) | MetaAPI UAT + distribution | Join MetaAPI UAT session; note product gaps | Live MetaAPI MT5 connect UAT; sync → dashboard balance check | Connected-accounts empty states; Safari login QA ¦ FE DONE 2026-08-02 (repo+prod deploy) | Recruit 2 trader friends for tomorrow's broker test; community channel rules pinned | Blog #2 draft; LinkedIn/X post announcing blog #1 | TODAY: Trial race-condition fix validated locally. MetaAPI/Get Bots UAT OPEN. Sheet sync applied. | Partial — aaradhya FE eng complete 2026-08-02
11 | 2026-07-31 | Fri | W2 — Prove live (M1–M4) | Coach live + outreach starts | Coach Insights admin check; decide beta allowlist draft emails (internal) | AI Coach live keys test; Coach Insights migration confirm | Alpha Coach UI empty states; help page structure for FAQs later ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach email #1–3 (brokers/creators) | Blog #2 revise; start blog #3 AI Coach outline; social post #2 | Coach stream works; 3 outreach emails | Partial — aaradhya FE eng complete 2026-08-02
12 | 2026-08-01 | Sat | W2 — Prove live (M1–M4) | W2 ship day | Friday deploy window approve; W2 review 45m | Stabilize any UAT bugs; uptime alert test fire | Ship remaining SEO fixes; Lighthouse re-measure home mobile ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach #4–6; invite 10 people to Discord (soft) | Publish blog #2; FAQ list of 15 topics drafted | LCP improved number recorded; blog #2 live | Partial — aaradhya FE eng complete 2026-08-02
13 | 2026-08-02 | Sun | W2 — Prove live (M1–M4) | Hardening + content | Saturday: legal pages skim for sign-off gaps | Wallet smoke test; rate-limit smoke on login/register | Cookie/banner check; OG images brief from ishit assets ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prospect CRM hygiene; note replies from outreach | Blog #3 draft; write 3 FAQ answers | Security smokes; FAQ started | Partial — aaradhya FE eng complete 2026-08-02
14 | 2026-08-03 | Mon | W2 — Prove live (M1–M4) | W2 close — M1–M4 largely green | Sunday: update Launch Countdown statuses; plan dogfood cohort of 5 | Rest / critical bugs only | Rest / critical UI only ¦ FE DONE 2026-08-02 (repo+prod deploy) | Light: community engagement 30m | Publish blog #3 OR schedule Mon; social posts #3–4 written | 3 blogs path complete; UAT evidence pack | Partial — aaradhya FE eng complete 2026-08-02
15 | 2026-08-04 | Tue | W3 — Dogfood + beta prep (M5) | Dogfood starts; invite copy ready | Internal dogfood kickoff: invite 5 (team+friends); set feedback form | Support dogfood: fix P0 bugs from day; paper trading path check | Onboarding flow polish; risk page UX ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prepare invite email list (20 names from top prospects); Discord onboarding message | Write beta invite email copy + welcome email #1 | 5 dogfood users active | Partial — aaradhya FE eng complete 2026-08-02
16 | 2026-08-05 | Wed | W3 — Dogfood + beta prep (M5) | Bug burn-down + email sequence | Triage dogfood feedback; prioritize P0/P1 board | P0 backend fixes (sync/auth/payments leftovers) | P0 frontend fixes from dogfood ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership outreach #7–10; soft ask for beta interest | Welcome email #2–3 copy; MT5 connect guide outline | P0 list shrinking; welcome sequence drafted | Partial — aaradhya FE eng complete 2026-08-02
17 | 2026-08-06 | Thu | W3 — Dogfood + beta prep (M5) | Allowlist + beta shortlist | Set BETA_ALLOWLIST_EMAILS for dogfood→beta; legal sign-off schedule | Allowlist wiring verify; notification emails for beta | Community page CTAs + Discord links live on site ¦ FE DONE 2026-08-02 (repo+prod deploy) | Confirm 20 beta candidates verbally/DM; track yes/maybe/no | Write MT5 connect guide draft; 5 more FAQ answers | Allowlist live; 20 candidates contacted | Partial — aaradhya FE eng complete 2026-08-02
18 | 2026-08-07 | Fri | W3 — Dogfood + beta prep (M5) | Legal + DR + help content | Legal sign-off Privacy/Terms/Risk (or lawyer note) | Backup restore drill (record date in docs) | Help center page updates for top FAQs (implement ishit text) ¦ FE DONE 2026-08-02 (repo+prod deploy) | India GTM notes (Razorpay messaging); growth report template | Finalize MT5 guide; social post #5–6 | Legal signed; restore dated | Partial — aaradhya FE eng complete 2026-08-02
19 | 2026-08-08 | Sat | W3 — Dogfood + beta prep (M5) | Beta-ready checkpoint | Friday: dogfood retro; GO/NO-GO for Mon beta invites | Copy-trading subscribe dry-run on staging/prod | Dashboard polish from dogfood notes; mobile pass ¦ FE DONE 2026-08-02 (repo+prod deploy) | First weekly growth report (prospects, replies, channel size) | Publish MT5 guide; FAQ pack 10/15 done | GO decision for M6 | Partial — aaradhya FE eng complete 2026-08-02
20 | 2026-08-09 | Sun | W3 — Dogfood + beta prep (M5) | Invite ammo ready | Saturday: finalize invite list of 20 + backups 10 | Light: bot marketplace smoke | Light: publish any pending UI ¦ FE DONE 2026-08-02 (repo+prod deploy) | Personalize 20 invite notes (not blast) | Invite email FINAL; social teaser (no public spam) | 20 personalized invites queued | Partial — aaradhya FE eng complete 2026-08-02
21 | 2026-08-10 | Mon | W3 — Dogfood + beta prep (M5) | W3 close | Sunday rest / emergency only; emotional prep for beta week | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest / community light | Rest / schedule Mon send | Ready for closed beta | Partial — aaradhya FE eng complete 2026-08-02
22 | 2026-08-11 | Tue | W4 — Closed beta 20 (M6) | M6 — beta invites out | SEND 20 beta invites; monitor support channel personally 2h | On-call for signup/OTP/broker issues; hotfix ready | On-call UI; watch registration funnel in PostHog ¦ FE DONE 2026-08-02 (repo+prod deploy) | DM follow-ups to non-openers; welcome in Discord | Post 'beta welcome' content inside community only | 20 invites sent | Partial — aaradhya FE eng complete 2026-08-02
23 | 2026-08-12 | Wed | W4 — Closed beta 20 (M6) | Activation day | Track activation: who connected broker; unblock manually | MetaAPI issues triage for beta users | Onboarding drop-off fixes if funnel shows pain ¦ FE DONE 2026-08-02 (repo+prod deploy) | Help 5 users activate; log objections | Publish 2 FAQs that beta asked; social educational post | Broker-connect count rising | Partial — aaradhya FE eng complete 2026-08-02
24 | 2026-08-13 | Thu | W4 — Closed beta 20 (M6) | Listen + fix | Product calls with 3 beta users (15m each) | Fix top sync/balance bug from beta | Fix top UI confusion from beta ¦ FE DONE 2026-08-02 (repo+prod deploy) | Invite 5 more from waitlist if slots; partnership update | Case-study notes (with consent); Short/Reel script #1 | 3 interviews done | Partial — aaradhya FE eng complete 2026-08-02
25 | 2026-08-14 | Fri | W4 — Closed beta 20 (M6) | Content from real users | Update roadmap from interviews; kill 1 non-critical feature idea | Coach quality issues / tool failures triage | Empty-state + copy tweaks from ishit ¦ FE DONE 2026-08-02 (repo+prod deploy) | Community engagement challenge (share first win) | Record Short #1 (dashboard or coach); FAQ 15/15 | Short #1 recorded; FAQ complete | Partial — aaradhya FE eng complete 2026-08-02
26 | 2026-08-15 | Sat | W4 — Closed beta 20 (M6) | W4 metrics | Friday beta metrics review (activation %, SEV1=0?) | Stabilize; no risky deploys after 4pm | Ship FAQ page updates; CWV check ¦ FE DONE 2026-08-02 (repo+prod deploy) | Weekly growth report #2; referral ask to activated users | Publish Short #1; LinkedIn story from beta learnings (anonymized) | Activation rate logged | Partial — aaradhya FE eng complete 2026-08-02
27 | 2026-08-16 | Sun | W4 — Closed beta 20 (M6) | Support + nurture | Saturday: deep user support hour | P1 bugfixes | P1 UI fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Nurture maybe→yes prospects | Guide: Risk management draft start | P1 burn-down | Partial — aaradhya FE eng complete 2026-08-02
28 | 2026-08-17 | Mon | W4 — Closed beta 20 (M6) | W4 close — 20-user beta running | Sunday: plan expand-to-50 criteria | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Risk guide outline done | M6 achieved if ≥10 activated | Partial — aaradhya FE eng complete 2026-08-02
29 | 2026-08-18 | Tue | W5 — Expand toward 50 (M7) | Scale invites | Approve next 30 invites; set activation target >30% | Copy-trading + bots UAT leftovers for power users | Instrument time-to-first-broker events if missing ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send next invite wave (15) | Publish risk management guide | 35 total invited path | Partial — aaradhya FE eng complete 2026-08-02
30 | 2026-08-19 | Wed | W5 — Expand toward 50 (M7) | Insights-driven eng | Coach Insights weekly ritual #1 | Improve coach responses for top thumbs-down intents | Analytics pages UX polish if users care ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send invite wave (15 more) → ~50 invited | Social posts #7–8; reply to all comments | ~50 invites out | Partial — aaradhya FE eng complete 2026-08-02
31 | 2026-08-20 | Thu | W5 — Expand toward 50 (M7) | Partnerships + perf | Partnership close calls (2) | Performance: API slow endpoints from beta usage | Frontend performance on dashboard ¦ FE DONE 2026-08-02 (repo+prod deploy) | Creator/broker collab draft agreement notes | Case study draft v1 (1 user) | 2 partner calls | Partial — aaradhya FE eng complete 2026-08-02
32 | 2026-08-21 | Fri | W5 — Expand toward 50 (M7) | Retention focus | Review churn/inactive beta users; win-back plan | Notification reliability (trade alerts email) | Settings/support ticket UX ¦ FE DONE 2026-08-02 (repo+prod deploy) | Win-back DMs to inactive; community AMA announce | AMA announcement creative; Short #2 script | Win-back started | Partial — aaradhya FE eng complete 2026-08-02
33 | 2026-08-22 | Sat | W5 — Expand toward 50 (M7) | Community proof | Friday: 50-user checkpoint vs activation KPI | Bugfix day from AMA prep | Ship pending UI; prepare demo environment ¦ FE DONE 2026-08-02 (repo+prod deploy) | Host community AMA / office hours | Record Short #2 during/after AMA | AMA done; activation % reported | Partial — aaradhya FE eng complete 2026-08-02
34 | 2026-08-23 | Sun | W5 — Expand toward 50 (M7) | Content + fixes | Saturday support coverage | P1 fixes | P1 fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Follow-ups from AMA | Publish Short #2; polish case study | Case study near-final | Partial — aaradhya FE eng complete 2026-08-02
35 | 2026-08-24 | Mon | W5 — Expand toward 50 (M7) | W5 close | Sunday: plan load-test week; declare M7 status | Rest / prepare load test env | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Rest / schedule posts | M7: toward 50 activated trajectory | Partial — aaradhya FE eng complete 2026-08-02
36 | 2026-08-25 | Tue | W6 — Harden + load (M8) | Load test day | Authorize load test window; freeze feature work (bugs only) | Run k6 load:d7:100 against healthy API; capture report | Fix frontend errors under load if any; monitor RUM ¦ FE DONE 2026-08-02 (repo+prod deploy) | No big campaigns (stability week); nurture only | Publish case study; educational posts only | Load report attached | Partial — aaradhya FE eng complete 2026-08-02
37 | 2026-08-26 | Wed | W6 — Harden + load (M8) | Perf fixes | Review load failures; prioritize fixes | Fix load bottlenecks (DB/redis/timeouts) | Reduce chatty client polling if found ¦ FE DONE 2026-08-02 (repo+prod deploy) | Quiet growth: 5 high-quality invites only | Blog refresh/internal links pass with aaradhya notes | p95 improved | Partial — aaradhya FE eng complete 2026-08-02
38 | 2026-08-27 | Thu | W6 — Harden + load (M8) | M8 evidence | Re-run load test subset; backup drill if not done | Second load pass OR restore drill evidence | SEO internal linking code; image alts ¦ FE DONE 2026-08-02 (repo+prod deploy) | Referral program messaging soft launch to beta | 2 posts on referral/value; FAQ updates | Load pass or clear gap list | Partial — aaradhya FE eng complete 2026-08-02
39 | 2026-08-28 | Fri | W6 — Harden + load (M8) | Security week | Security checklist D2 review with sunish | Secret rotation remaining; security Playwright suite | Security-sensitive UI (API keys settings) review ¦ FE DONE 2026-08-02 (repo+prod deploy) | Partnership pipeline update doc | Trust content: risk disclosure explainer social | D2 checklist advanced | Partial — aaradhya FE eng complete 2026-08-02
40 | 2026-08-29 | Sat | W6 — Harden + load (M8) | M8 checkpoint | Friday: GO/NO-GO for push to 100 | Stabilize; document runbooks gaps closed | Status page polish; public trust signals ¦ FE DONE 2026-08-02 (repo+prod deploy) | Prepare 50 more prospect outreaches for next week | Content calendar for scale week | GO for M9 or fix list | Partial — aaradhya FE eng complete 2026-08-02
41 | 2026-08-30 | Sun | W6 — Harden + load (M8) | Prep scale | Saturday: ops dry-run of invite-to-100 process | Light fixes | Light fixes ¦ FE DONE 2026-08-02 (repo+prod deploy) | Segment prospect list for 100 | Batch social assets | Invite ops ready | Partial — aaradhya FE eng complete 2026-08-02
42 | 2026-08-31 | Mon | W6 — Harden + load (M8) | W6 close | Sunday rest | Rest | Rest ¦ FE DONE 2026-08-02 (repo+prod deploy) | Rest | Rest | M8 ideally green | Partial — aaradhya FE eng complete 2026-08-02
43 | 2026-09-01 | Tue | W7 — Scale to 100 (M9) | Scale start | Open scale: approve invites toward 100 users | Capacity watch; auto-scale/min instances tune | Funnel UX final polish for new users ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send large invite wave (batch 1 of 2) | Launch content burst: 1 blog remix + 3 socials | User count climbing | Partial — aaradhya FE eng complete 2026-08-02
44 | 2026-09-02 | Wed | W7 — Scale to 100 (M9) | Push to 100 | Daily activation standup 15m; unblock stuck users | Hotfixes only; MetaAPI quotas watch | Hotfixes only; onboarding tweaks ¦ FE DONE 2026-08-02 (repo+prod deploy) | Send batch 2 invites; partnerships announce if ready | User-story posts (consented); Short #3 | ~100 invited / approaching 100 active | Partial — aaradhya FE eng complete 2026-08-02
45 | 2026-09-03 | Thu | W7 — Scale to 100 (M9) | 45-day finish line | DAY 45 REVIEW: score M0–M9; decide open growth vs stay closed; update sheet | Write eng retro: what broke, what held; next 30d eng backlog | Write web/UX retro; CWV final numbers ¦ FE DONE 2026-08-02 (repo+prod deploy) | Growth retro: CAC proxy, best channels, next 30d acquisition plan | Content retro: top posts; next 30d editorial calendar | Written retros + 100-user status + next plan | Partial — aaradhya FE eng complete 2026-08-02

## How to use Daily 10h
HOW TO USE — Daily 10h Tasks
This is not AI fluff. Each row is a real block of work with a proof of done.
Filter column Person = your name. Sort by Day, then Block.
Weekdays target ~10 hours (09:00 start, lunch break after ~5h of work, resume 14:00).
Sundays are ~6 hours max — real humans rest or only do light ops.
Tick Done? = Y only when 'Done when' proof exists (screenshot, link, message, file).
If you slip a block, move it to Notes and steal from Buffer — don't silently skip EOD proof.
Marketing starts at ZERO on Day 1 (kushwaha + ishit). No fake 'already posting'.
Coding = sunish + aaradhya. abhishek jumps in as all-rounder.
Quick filters:
Day 1–7 Stabilize ¦ 8–14 Prove UAT ¦ 15–21 Dogfood ¦ 22–28 Beta20 ¦ 29–35 Expand50 ¦ 36–42 Harden ¦ 43–45 Scale100
Total task rows: 1283
Day 1 date: 2026-07-21 ¦ Day 45: 2026-09-03

## 45 Day Summary
PROFYTRON — 45 DAY PLAN SUMMARY (Marketing starts at ZERO)
Day 1 starts 2026-07-21 · Coding: sunish + aaradhya (+ abhishek) · Marketing: kushwaha + ishit from absolute zero
Days | Phase | Engineering must finish | Marketing from zero | Milestone exit
1–7 | W1 Stabilize | GCP API up DONE; backups DONE; Sentry DONE; /status DONE; OTP self-test DONE. LCP started (not signed off). Marketing — NO evidence. | ICP, prospect CRM 0→80, brand voice, hero copy v1, blog#1 draft, social calendar skeleton, competitor teardown | M0 in progress; marketing no longer zero
8–14 | W2 Prove live | OTP UAT PASS. Payments + MetaAPI/Get-Bots UAT OPEN. Trial code local-ready. SEO robots/sitemap DONE. Blogs — NO evidence. | Prospects/Discord/blogs/outreach — NO evidenced completion; keep Not Started until proof | M1–M4 mostly green
15–21 | W3 Dogfood | 5 dogfood users; P0 fixes; allowlist; restore drill; legal; onboarding polish | Invite list 20 personalized; welcome emails; MT5 guide; FAQ 10+; growth report #1 | M5 green; ready for invites
22–28 | W4 Beta 20 | On-call hotfixes; activation unblocks; sync bugs; FAQ pages shipped | 20 invites sent; Discord active; interviews support; Short#1; referral ask | M6: ≥10 activated ideal
29–35 | W5 Expand 50 | Copy-trade/bots polish; PostHog activation events; perf fixes; Coach Insights ritual | Invites → ~50; AMA; risk guide; Short#2; case study; win-backs | M7 trajectory
36–42 | W6 Harden | k6 100 VU pass; bottlenecks; security D2; runbooks; feature freeze | Quiet nurture; case study publish; referral soft launch; prep scale list | M8 green
43–45 | W7 Scale 100 | Capacity watch; hotfixes only; retros | Invite waves to 100; content burst; growth + content retros | M9 status + next 30d plan
MARKETING ZERO → HERO METRICS
Day 1: 0 prospects, 0 posts, 0 blogs, 0 community, 0 outreach
Day 7: ~80 prospects, hero copy, blog draft, calendar skeleton
Day 14: 100 prospects, 3 blogs path, Discord live, outreach started
Day 21: 20 personalized invites ready, welcome emails, MT5 guide
Day 28: 20 invited, community active, Short#1, activation tracked
Day 35: ~50 invited, AMA done, case study, Short#2
Day 45: push to 100 users + retros
NON-NEGOTIABLE ORDER
1) API up DONE 2) Live UAT (OTP DONE → Pay OPEN → Get Bots/MetaAPI OPEN) 3) Web LCP+/status(/status DONE) 4) Marketing engine 5) Dogfood 5 6) Beta 20 7) 50 8) Load pass 9) 100
Do not invite 100 users before Days 36–42 load/security hardening.

## Settings (1)
Team Member | Role | Department | Primary Focus | Sprint Capacity (hrs/wk) | Owns | Does NOT Do
abhishek | CEO / All-Rounder | Product + Engineering | Product decisions, priorities, beta, legal, partnerships + jumps into coding/infra/reviews when needed | 50 | Executive Dashboard, Launch Countdown, Weekly Review, critical eng reviews | Nothing off-limits — but default eng work goes to sunish/aaradhya
sunish | Engineer — Infra, Trading, AI | Engineering | GCP/Cloud Run, MetaAPI, bots, copy trading, AI Coach, sync pipeline, load tests, Sentry, backups | 45 | Deployment Tracker, Trading/Coach features, load/UAT eng | Marketing content / social
aaradhya | Engineer — Frontend, Web, Product UI | Engineering | Frontend/UI, landing LCP, /status, onboarding UX, dashboard polish, web SEO implementation, PostHog wiring, marketing-page code | 45 | Feature Matrix (web), Website eng, Testing (UI), SEO code fixes | Social posting / blog writing
abhishek kushwaha | Marketing — Growth & Acquisition | Marketing | User acquisition, partnerships, beta invites, community growth, campaigns, prospect lists, competitor intel | 45 | Marketing Plan (growth), KPI acquisition, community | Coding / deploys
ishit | Marketing — Content & Brand | Marketing | Blogs, guides, social, website copy, brand voice, email copy, FAQs, Shorts/creatives | 45 | SEO Tracker (content), Marketing Plan (content), Website Checklist (copy) | Coding / deploys
Quick rule | Detail
Coding | sunish + aaradhya (+ abhishek when needed)
Marketing | abhishek kushwaha (growth) + ishit (content)
Product lead | abhishek (all-rounder)
Phase | Planning ¦ Development ¦ Testing ¦ Deployment ¦ Marketing ¦ Ops
Priority | Critical ¦ High ¦ Medium ¦ Low
Status | Not Started ¦ In Progress ¦ Review ¦ Blocked ¦ Completed ¦ Deferred
Task Type | Epic ¦ Feature ¦ Bug ¦ Chore ¦ UAT ¦ Ops ¦ Content ¦ SEO ¦ Campaign ¦ Support

## Master Tracker (1)
Task ID | Task Name | Owner | Phase | Department | Sprint | Priority | Status | Risk Level | Task Type | Estimated Hours | Actual Hours | Notes / Evidence
PT-E01 | Track D — Launch Readiness (live ops proofs) | abhishek | Ops | Product | Sprint 1 | Critical | In Progress | Critical | Epic | 30 | 8 | All-rounder owns gate; eng executes
PT-E02 | Closed Beta 20–50 users | abhishek | Ops | Product | Sprint 2 | Critical | Not Started | High | Epic | 25 | 0 | CLOSED_BETA_PLAYBOOK.md
PT-E03 | Scale to 100 users | abhishek | Ops | Product | Sprint 4 | High | Not Started | High | Epic | 20 | 0
PT-E04 | Marketing engine for acquisition | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Epic | 60 | 0 | Growth lead; ishit content
PT-D01 | Pick primary production backend (GCP Cloud Run) | sunish | Deployment | Engineering | Sprint 1 | Critical | In Progress | Critical | Ops | 6 | 3 | abhishek final approve
PT-D02 | Deploy API to GCP Cloud Run min-instances=1 | sunish | Deployment | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 12 | 0
PT-D03 | Deploy Web + ship /status to prod | aaradhya | Deployment | Engineering | Sprint 1 | Critical | Not Started | High | Ops | 8 | 0 | Frontend/web owner
PT-D04 | Verify /live /ready /health = 200 on prod API | sunish | Deployment | Engineering | Sprint 1 | Critical | Blocked | Critical | UAT | 4 | 1 | Failed 2026-07-19
PT-D05 | Wire Sentry DSN API + Web | sunish | Deployment | Engineering | Sprint 1 | High | Not Started | High | Ops | 3 | 0 | aaradhya verifies web DSN
PT-D06 | Enable Cloud SQL backups + remove duplicate instance | sunish | Deployment | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 6 | 0
PT-D07 | DB backup restore drill + record date | sunish | Ops | Engineering | Sprint 2 | High | Not Started | High | Ops | 6 | 0
PT-D08 | Uptime alerts on /health | sunish | Ops | Engineering | Sprint 1 | High | Not Started | High | Ops | 4 | 0
PT-D09 | Write deploy RUNBOOK (single source of truth) | abhishek | Ops | Product | Sprint 1 | Medium | Not Started | Medium | Chore | 3 | 0 | All-rounder docs; sunish fills commands
PT-D10 | Re-run k6 load test 100 VUs | sunish | Testing | Engineering | Sprint 2 | Critical | Blocked | Critical | UAT | 8 | 2
PT-A01 | Live email OTP UAT (Resend inbox proof) | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 8 | 0
PT-A02 | SPF/DKIM/DMARC for sending domain | sunish | Ops | Engineering | Sprint 1 | Critical | Not Started | High | Ops | 4 | 0
PT-A03 | EXPOSE_DEV_OTP OFF in production | sunish | Ops | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 1 | 0 | abhishek verifies
PT-A04 | Safari/iOS login + refresh cookie fix/QA | aaradhya | Testing | Engineering | Sprint 1 | High | Not Started | High | Bug | 6 | 0 | Frontend auth
PT-A05 | Google + GitHub OAuth smoke test | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 4 | 0
PT-A06 | 2FA enroll + login smoke test | sunish | Testing | Engineering | Sprint 2 | Medium | Not Started | Medium | UAT | 3 | 0
PT-A07 | Forgot/reset password end-to-end | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 3 | 0
PT-A08 | Set BETA_ALLOWLIST_EMAILS in prod | abhishek | Ops | Product | Sprint 2 | Critical | Not Started | High | Ops | 2 | 0 | All-rounder applies or directs sunish
PT-A09 | Auth journey UI polish (verify-email screens) | aaradhya | Development | Engineering | Sprint 1 | Medium | Not Started | Low | Feature | 4 | 0
PT-P01 | Live Stripe/Razorpay checkout UAT | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 10 | 0
PT-P02 | Webhook → entitlement proof | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 6 | 0
PT-P03 | Billing UI polish + plan cards | aaradhya | Development | Engineering | Sprint 1 | High | Not Started | Medium | Feature | 5 | 0 | Implements ishit's copy
PT-P04 | Wallet smoke test | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 6 | 0
PT-P05 | Pricing messaging strategy / A/B ideas | abhishek kushwaha | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Campaign | 4 | 0
PT-T01 | Live MetaAPI MT5 connect UAT | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 12 | 0
PT-T02 | Account sync → dashboard balance proof | sunish | Testing | Engineering | Sprint 1 | Critical | Not Started | Critical | UAT | 8 | 0
PT-T03 | Copy trading subscribe UAT | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 10 | 0
PT-T04 | Bot marketplace → active bot UAT | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 8 | 0
PT-T05 | Paper trading path for new users | sunish | Development | Engineering | Sprint 2 | High | Not Started | Medium | Feature | 8 | 0
PT-T06 | WebSocket gateway stability under load | sunish | Testing | Engineering | Sprint 2 | High | Not Started | High | UAT | 6 | 0
PT-T07 | Connected-accounts / copy-trading UI polish | aaradhya | Development | Engineering | Sprint 2 | High | Not Started | Medium | Feature | 8 | 0
PT-T08 | Recruit 5 traders for MetaAPI beta testing | abhishek kushwaha | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Campaign | 8 | 0
PT-C01 | AI Coach live stream with prod keys | sunish | Testing | Engineering | Sprint 1 | High | Not Started | Medium | UAT | 6 | 0
PT-C02 | Coach Insights migration + admin confirm | sunish | Deployment | Engineering | Sprint 1 | High | Not Started | Medium | Ops | 4 | 0 | abhishek reviews admin
PT-C03 | Alpha Coach UI polish + empty states | aaradhya | Development | Engineering | Sprint 2 | Medium | Not Started | Low | Feature | 5 | 0
PT-C04 | AI Coach explainer content + FAQ copy | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 8 | 0
PT-W01 | Landing LCP < 4s (lazy-load 3D/motion) | aaradhya | Development | Engineering | Sprint 1 | Critical | Not Started | High | Feature | 16 | 0 | Frontend perf
PT-W02 | Mobile responsive QA all public pages | aaradhya | Testing | Engineering | Sprint 1 | High | In Progress | Medium | Chore | 10 | 3
PT-W03 | Implement approved homepage hero/CTA in code | aaradhya | Development | Engineering | Sprint 1 | Critical | Not Started | Medium | Feature | 4 | 0 | After ishit copy
PT-W04 | Rewrite homepage hero + CTA copy | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 6 | 0
PT-W05 | Pricing page copy | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 5 | 0
PT-W06 | Onboarding + risk page UX/code polish | aaradhya | Development | Engineering | Sprint 2 | High | Not Started | Medium | Feature | 8 | 0
PT-W07 | Onboarding copy | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 4 | 0
PT-W08 | OG/PWA image assets implementation | aaradhya | Development | Engineering | Sprint 2 | Low | Not Started | Low | Chore | 3 | 0 | ishit briefs assets
PT-S01 | Verify sitemap/robots on prod + fix if broken | aaradhya | Marketing | Engineering | Sprint 1 | High | Not Started | Medium | SEO | 3 | 0 | Code-side SEO
PT-S02 | Submit sitemap to Google Search Console | abhishek | Marketing | Product | Sprint 1 | High | Not Started | Medium | SEO | 2 | 0 | All-rounder sets up GSC access; can hand to aaradhya
PT-S03 | Title/meta/OG audit + code fixes on key pages | aaradhya | Marketing | Engineering | Sprint 1 | High | Not Started | Medium | SEO | 6 | 0 | ishit provides copy where needed
PT-S04 | JSON-LD Rich Results validation + fixes | aaradhya | Marketing | Engineering | Sprint 1 | Medium | Not Started | Low | SEO | 3 | 0
PT-S05 | Write + publish: What is Copy Trading | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 10 | 0
PT-S06 | Write + publish: MT5 Automation with Profytron | ishit | Marketing | Marketing | Sprint 1 | Critical | Not Started | Medium | Content | 10 | 0
PT-S07 | Write + publish: AI Trading Coach explained | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 10 | 0
PT-S08 | Write guide: Connect MT5 step-by-step | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0
PT-S09 | Write guide: Risk management for copy traders | ishit | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Content | 8 | 0
PT-S10 | Brokers hub content + page SEO improvements | aaradhya | Marketing | Engineering | Sprint 2 | High | Not Started | Medium | SEO | 8 | 0 | ishit writes; aaradhya ships
PT-S11 | Internal linking implementation | aaradhya | Marketing | Engineering | Sprint 2 | Medium | Not Started | Low | SEO | 4 | 0
PT-S12 | Maintain SEO Tracker weekly | ishit | Marketing | Marketing | Sprint 1 | High | In Progress | Medium | SEO | 3 | 1 | Keywords + content status
PT-S13 | Competitor keyword & landing teardown | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Campaign | 8 | 0 | Feeds ishit/aaradhya
PT-M01 | Wire PostHog in production (code) | aaradhya | Ops | Engineering | Sprint 1 | Critical | Not Started | High | Ops | 5 | 0 | Frontend analytics
PT-M02 | Define activation funnel with abhishek | abhishek | Planning | Product | Sprint 1 | High | Not Started | Medium | Chore | 3 | 0 | aaradhya implements events
PT-M03 | Beta invite + welcome email copy (3 emails) | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0 | sunish/aaradhya wire Resend if needed
PT-M04 | Set up Discord/Telegram beta community | abhishek kushwaha | Ops | Marketing | Sprint 2 | Critical | Not Started | High | Campaign | 6 | 0
PT-M05 | Social calendar 12 posts (LinkedIn/X) | ishit | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Content | 10 | 0
PT-M06 | Record 3 YouTube Shorts / Reels | ishit | Marketing | Marketing | Sprint 2 | Medium | Not Started | Low | Content | 10 | 0
PT-M07 | Press kit /press content refresh | ishit | Marketing | Marketing | Sprint 3 | Low | Not Started | Low | Content | 5 | 0
PT-M08 | Community page CTAs + invite links | aaradhya | Development | Engineering | Sprint 2 | Medium | Not Started | Low | Feature | 3 | 0 | Links from growth
PT-M09 | Partnership outreach: 10 brokers/creators | abhishek kushwaha | Marketing | Marketing | Sprint 1 | High | Not Started | Medium | Campaign | 12 | 0 | abhishek joins key calls
PT-M10 | Beta waitlist / invite list of 100 prospects | abhishek kushwaha | Marketing | Marketing | Sprint 1 | Critical | Not Started | High | Campaign | 10 | 0
PT-M11 | Help center top 15 FAQs rewrite | ishit | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Content | 8 | 0
PT-M12 | Weekly growth report | abhishek kushwaha | Marketing | Marketing | Sprint 2 | High | Not Started | Medium | Campaign | 3 | 0
PT-M13 | Referral messaging for beta users | abhishek kushwaha | Marketing | Marketing | Sprint 3 | Medium | Not Started | Low | Campaign | 4 | 0
PT-M14 | India GTM angle (Razorpay, local posts) | abhishek kushwaha | Marketing | Marketing | Sprint 2 | Medium | Not Started | Medium | Campaign | 6 | 0 | ishit assets
PT-M15 | Contact form → support reply process | abhishek | Ops | Product | Sprint 1 | High | Not Started | Medium | Support | 2 | 0 | All-rounder owns ops process
PT-L01 | Legal sign-off Privacy + Terms + Risk | abhishek | Ops | Product | Sprint 2 | High | Not Started | High | Chore | 4 | 0
PT-L02 | Cookie banner / policy UX check | aaradhya | Testing | Engineering | Sprint 2 | Medium | Not Started | Medium | Feature | 3 | 0
PT-L03 | Support SLA + on-call rotation | abhishek | Ops | Product | Sprint 2 | High | Not Started | High | Ops | 3 | 0
PT-L04 | Chatbot keys + FAQ content pack wiring | aaradhya | Ops | Engineering | Sprint 2 | Medium | Not Started | Low | Ops | 4 | 0 | ishit writes FAQ pack
PT-X01 | Security checklist D2 + secret rotation | sunish | Ops | Engineering | Sprint 2 | High | Not Started | High | Ops | 8 | 0 | abhishek reviews
PT-X02 | Security Playwright suite + evidence | sunish | Testing | Engineering | Sprint 2 | High | Not Started | Medium | UAT | 6 | 0
PT-X03 | Rotate AES_MASTER_KEY + JWT for prod | sunish | Ops | Engineering | Sprint 1 | Critical | Not Started | Critical | Ops | 3 | 0
PT-X04 | Rate-limit smoke test register/login | sunish | Testing | Engineering | Sprint 1 | Medium | Not Started | Medium | UAT | 2 | 0
PT-K01 | Lock KPI targets for beta | abhishek | Planning | Product | Sprint 1 | High | Not Started | Medium | Chore | 3 | 0
PT-K02 | Weekly Coach Insights review | abhishek | Ops | Product | Sprint 3 | Medium | Not Started | Low | Ops | 2 | 0
PT-K03 | Instrument time-to-first-broker in PostHog | aaradhya | Marketing | Engineering | Sprint 2 | High | Not Started | Medium | Feature | 3 | 0
PT-R01 | Daily standup logged every weekday | abhishek | Ops | Product | Sprint 1 | Medium | Not Started | Low | Chore | 5 | 0
PT-R02 | Friday Weekly Review | abhishek | Ops | Product | Sprint 1 | Medium | Not Started | Low | Chore | 2 | 0
PT-R03 | Keep Executive Dashboard updated | abhishek | Ops | Product | Sprint 1 | High | Not Started | Low | Chore | 2 | 0
PT-E05 | Code review critical PRs (auth/payments/MetaAPI) | abhishek | Ops | Engineering | Sprint 1 | High | Not Started | Medium | Chore | 6 | 0 | All-rounder eng oversight
PT-E06 | Pair on production incident response | abhishek | Ops | Engineering | Sprint 1 | High | Not Started | High | Ops | 4 | 0 | With sunish/aaradhya as needed
PT-Z01 | Track B Strategy Builder build | sunish | Planning | Engineering | Backlog | Low | Deferred | Low | Epic | 80 | 0 | aaradhya UI when opened
PT-Z02 | Track C Marketplace growth features | abhishek | Planning | Product | Backlog | Low | Deferred | Low | Epic | 40 | 0
PT-Z03 | External Statuspage | sunish | Ops | Engineering | Backlog | Low | Deferred | Low | Ops | 6 | 0
PT-Z04 | Open GA registration (no allowlist) | abhishek | Ops | Product | Backlog | Medium | Deferred | High | Ops | 4 | 0
PT-Z05 | Affiliate soft launch | abhishek kushwaha | Marketing | Marketing | Backlog | Low | Deferred | Low | Campaign | 10 | 0

## Feature Matrix (1)
Feature ID | Feature Name | Eng Owner | Marketing Owner | Code Status | Live Proof | Content Status | Overall | Notes
F-01 | Marketing website | aaradhya | ishit | Completed | Partial | Partial | Partial | LCP = aaradhya; copy = ishit
F-02 | SEO system | aaradhya | ishit | Completed | Partial | Not Started | Partial | Code SEO = aaradhya
F-03 | Blog + Guides | aaradhya | ishit | Completed | Partial | Not Started | Partial
F-04 | Brokers hub | aaradhya | ishit | Completed | Partial | Partial | Partial
F-05 | Auth + OTP | sunish | — | Completed | Blocked | N/A | Blocked | aaradhya UI polish
F-06 | OAuth | sunish | — | Completed | Not Started | N/A | Partial
F-07 | 2FA + magic link | sunish | — | Completed | Not Started | N/A | Partial
F-08 | Closed beta allowlist | abhishek | abhishek kushwaha | Completed | Not Started | N/A | Not Started
F-09 | Billing | sunish | abhishek kushwaha | Completed | Blocked | Partial | Blocked | UI = aaradhya
F-10 | Wallet | sunish | — | Completed | Not Started | N/A | Partial
F-11 | Dashboard | aaradhya | ishit | Completed | Partial | Partial | Partial
F-12 | MT5 / Connected accounts | sunish | abhishek kushwaha | Completed | Blocked | Not Started | Blocked | UI = aaradhya
F-13 | Copy trading | sunish | ishit | Completed | Not Started | Not Started | Partial
F-14 | Bots marketplace | sunish | abhishek kushwaha | Completed | Not Started | Partial | Partial
F-15 | AI Coach | sunish | ishit | Completed | Partial | Not Started | Partial | UI = aaradhya
F-16 | Coach Insights | sunish | abhishek | Completed | Not Started | N/A | Not Started
F-17 | Notifications | sunish | ishit | Completed | Not Started | Partial | Partial
F-18 | Support + chatbot | aaradhya | ishit | Completed | Not Started | Partial | Partial
F-19 | Help / Docs | aaradhya | ishit | Completed | Partial | Partial | Partial
F-20 | Legal pages | aaradhya | abhishek | Completed | Partial | Completed | Partial
F-21 | Status page | aaradhya | — | Completed | Blocked | N/A | Blocked
F-22 | PostHog | aaradhya | abhishek | Completed | Not Started | N/A | Not Started
F-23 | Sentry | sunish | — | Completed | Not Started | N/A | Not Started
F-24 | CI/CD + GCP | sunish | — | Completed | Partial | N/A | Partial | abhishek reviews
F-25 | Strategy Builder | sunish | — | Partial | Deferred | N/A | Deferred
F-26 | Affiliate | aaradhya | abhishek kushwaha | Completed | Deferred | Not Started | Deferred

## SEO Tracker (1)
Keyword | Volume | Difficulty | Landing Page | Rank | Target | Status | Content Owner | Eng SEO Owner | Priority | Notes
copy trading platform | High | High | /pricing | NR | Top 10 | Not Started | ishit | aaradhya | Critical
best copy trading software | High | High | /pricing | NR | Top 10 | Not Started | ishit | aaradhya | Critical
MT5 copy trading | High | Medium | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Critical
MetaTrader 5 automation | Medium | Medium | /blog | NR | Top 10 | Not Started | ishit | aaradhya | High
AI trading coach | Medium | Low | /blog | NR | Top 5 | Not Started | ishit | aaradhya | High
how to connect MT5 to copy trading | Medium | Low | /guides | NR | Top 3 | Not Started | ishit | aaradhya | Critical
what is copy trading | High | Medium | /blog | NR | Top 5 | Not Started | ishit | aaradhya | Critical
Profytron | Brand | Low | / | NR | 1 | Not Started | ishit | aaradhya | Critical
Profytron pricing | Brand | Low | /pricing | NR | 1 | Not Started | ishit | aaradhya | High
social trading platform India | Medium | Medium | / | NR | Top 10 | Not Started | ishit | aaradhya | High | From growth
best MT5 brokers for copy trading | Medium | Medium | /brokers | NR | Top 10 | Not Started | ishit | aaradhya | High
automated forex trading bots | High | High | /marketplace | NR | Top 20 | Not Started | ishit | aaradhya | High
paper trading MT5 | Medium | Low | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Medium
risk management copy trading | Medium | Low | /guides | NR | Top 5 | Not Started | ishit | aaradhya | Medium
trading bot marketplace | Medium | Medium | /marketplace | NR | Top 15 | Not Started | ishit | aaradhya | Medium
Exness copy trading | Medium | Medium | /brokers | NR | Top 10 | Not Started | ishit | aaradhya | Medium | Competitor input
Razorpay trading subscription | Low | Low | /pricing | NR | Top 5 | Not Started | ishit | aaradhya | Medium | India GTM
forex signal copy trading | Medium | Medium | /copy-trading | NR | Top 10 | Not Started | ishit | aaradhya | High
AI forex assistant | Low | Low | /blog | NR | Top 5 | Not Started | ishit | aaradhya | Medium
Profytron login | Brand | Low | /login | NR | 1 | Not Started | ishit | aaradhya | High

## Deployment Tracker (1)
Environment | Service | Status | Health Check | Owner | Backup Owner | Notes
Production | API (GCP Cloud Run) | Blocked | Failed historically | sunish | abhishek | Primary blocker
Production | Web + /status | Partial | /status was 404 | aaradhya | abhishek
Production | AI Coach | Partial | Unknown | sunish | abhishek
Production | Postgres | Partial | Backups risk | sunish | abhishek
Production | Redis | Partial | Unknown | sunish | abhishek
Legacy | Render free API | Blocked | Timeouts | sunish | abhishek | DECOMMISSION
CI | GitHub Actions | Healthy | PR checks | sunish | aaradhya

## Testing Dashboard (1)
Module | Primary Eng | Secondary | Marketing QA | Eng Status | Overall | Notes
Auth / OTP | sunish | aaradhya | ishit | Blocked | Blocked | UI QA = aaradhya
Payments | sunish | aaradhya | abhishek kushwaha | Blocked | Blocked
MetaAPI / Broker | sunish | abhishek | abhishek kushwaha | Blocked | Blocked
Copy Trading | sunish | aaradhya | ishit | Not Started | Not Started
Bots | sunish | aaradhya | abhishek kushwaha | Not Started | Not Started
AI Coach | sunish | aaradhya | ishit | Partial | Partial
Landing / Web | aaradhya | abhishek | ishit | Partial | Partial | LCP
SEO implementation | aaradhya | — | ishit | Partial | Partial
Load / API health | sunish | abhishek | — | Failed | Blocked
Security | sunish | abhishek | — | Not Started | Not Started
Dashboard UI | aaradhya | sunish | ishit | Partial | Partial

## KPI Dashboard (1)
KPI | Current | Target | Owner | Cadence | Notes
Task completion (excl deferred) | 0% | 100% | abhishek | Daily
API uptime 7d | Unknown | 99.5% | sunish | Daily | abhishek watches
Landing LCP mobile | ~50s | <4s | aaradhya | Weekly
OTP deliverability | Unproven | Pass | sunish | Once
MetaAPI connect success | Unproven | >95% | sunish | Weekly
Payment checkout success | Unproven | >95% | sunish | Weekly
Beta prospect list | 0 | 100 | abhishek kushwaha | Weekly
Beta invites sent | 0 | 50 | abhishek | Weekly
Activated users (broker) | 0 | 20 | abhishek kushwaha | Weekly
7-day activation rate | — | >30% | aaradhya | Weekly | PostHog
Blog posts published | 0 | 10 by W6 | ishit | Weekly
Social posts / week | 0 | 3 | ishit | Weekly
Partnerships started | 0 | 10 | abhishek kushwaha | Weekly
Load test 100 VU | Fail | Pass | sunish | Once

## Launch Countdown (1)
Milestone | Target Date | Days Left | Owner | Status | Definition of Done
M0 — Production API stable 24/7 | 2026-07-27 | 7 | sunish (+ abhishek) | Blocked | /health 200 for 48h
M1 — Live UAT OTP + Payments + MetaAPI | 2026-07-30 | 10 | sunish | Not Started | Track D evidence filed
M2 — /status + Sentry + monitoring | 2026-07-30 | 10 | aaradhya + sunish | Not Started | Public /status + alerts
M3 — LCP <4s + homepage copy live | 2026-08-03 | 14 | aaradhya + ishit | Not Started | Perf + approved copy
M4 — Marketing engine ready | 2026-08-03 | 14 | abhishek kushwaha + ishit | Not Started | 3 blogs, Discord, 100 prospects
M5 — Internal dogfood 5 users | 2026-08-05 | 16 | abhishek | Not Started | 0 SEV1
M6 — Closed beta 20 invites | 2026-08-10 | 21 | abhishek + abhishek kushwaha | Not Started | 20 invites + community
M7 — Expand to 50 | 2026-08-24 | 35 | abhishek kushwaha | Not Started | Activation >30%
M8 — Load test + backup drill | 2026-08-31 | 42 | sunish | Blocked | D7 pass
M9 — 100 users | 2026-09-14 | 56 | abhishek | Not Started | 100 users live
M10 — Open growth push | 2026-09-28 | 70 | abhishek kushwaha | Not Started | Campaigns live

## Daily Standup (1)
Date | Member | Yesterday | Today | Blockers | Priority | Status
2026-07-20 | abhishek | Clarified roles: all-rounder; aaradhya codes; marketing = kushwaha+ishit | Prioritize M0; GSC/allowlist plan; review eng blockers; partner calls | API still the gate | Critical | In Progress
2026-07-20 | sunish | Reviewed GCP + Track D health failures | Cloud Run API stable; backups; OTP/MetaAPI/Payment UAT prep | Prod API downtime history | Critical | In Progress
2026-07-20 | aaradhya | Role updated: Engineer (frontend/web) not marketing-only | Landing LCP plan; /status deploy; auth UI Safari QA; PostHog wiring plan | Need prod web access + design copy from ishit | Critical | In Progress
2026-07-20 | abhishek kushwaha | Growth marketing only (no coding) | 100-prospect list; competitor teardown; partnership outreach | Need positioning one-pager | High | In Progress
2026-07-20 | ishit | Content/brand marketing only (no coding) | Homepage/pricing copy; 3 blog outlines; social calendar | Need screenshots/product facts | High | In Progress

## Weekly Review (1)
Week | Dates | Goals | Eng Focus | Marketing Focus | Owner
W1 | 2026-07-20 → 2026-07-26 | M0 API up; UAT prep; web LCP start; marketing lists/copy | sunish: API/backups/Sentry · aaradhya: LCP,/status,PostHog · abhishek: reviews | kushwaha: prospects+outreach · ishit: copy+blogs outline | abhishek
W2 | 2026-07-27 → 2026-08-02 | Pass 3 live UATs; publish 3 blogs; community | sunish: OTP/Payments/MetaAPI · aaradhya: ship copy + SEO fixes | Publish content; Discord; partnerships | abhishek
W3 | 2026-08-03 → 2026-08-09 | Dogfood 5; allowlist; legal | Bugfixes from dogfood | Invites prep; FAQs; welcome emails | abhishek
W4 | 2026-08-10 → 2026-08-16 | Beta 20 live | Stability + copy-trading UAT | Invite campaign + support content | abhishek

## Sprint Board (1)
Sprint | Theme | Dates | sunish | aaradhya | abhishek | abhishek kushwaha | ishit | Status
Sprint 1 | Make it live | 2026-07-20 → 2026-08-02 | API, MetaAPI/OTP/Payments UAT, Sentry, backups, load prep | LCP, /status, Safari auth, PostHog, SEO code, billing UI | Priorities, reviews, GSC, allowlist plan, incidents | 100 prospects, partnerships, competitor teardown | Homepage/pricing copy, 3 blogs, social calendar | In Progress
Sprint 2 | Beta ready | 2026-08-03 → 2026-08-16 | Finish UATs, restore drill, trading UAT | Onboarding UX, community links, coach UI, cookies | Dogfood, legal, invites approve, on-call | Discord, invite ops, recruit test traders, growth report | Publish guides, welcome emails, Shorts, FAQs | Not Started
Sprint 3 | Scale 50 | 2026-08-17 → 2026-08-30 | Beta bugfixes, coach insights | Activation instrumentation, UI polish | Coach Insights review, priorities | Scale invites, referral, partnerships | More content + case studies | Not Started
Sprint 4 | 100 users | 2026-08-31 → 2026-09-13 | Load test pass, infra scale | Growth page tweaks | Go/no-go for 100 | Acquisition to 100 | Creative assets | Not Started

## Marketing Plan (1)
Week | Owner | Lane | Action | Status | KPI Impact | Eng Dependency
W1 | abhishek kushwaha | Growth | Build beta prospect list to 100 | Not Started | Invites ready | None
W1 | abhishek kushwaha | Growth | Competitor landing/pricing teardown | Not Started | Messaging | Share brief with ishit/aaradhya
W1 | abhishek kushwaha | Growth | Start 10 partnership outreach threads | Not Started | Pipeline | abhishek joins calls
W1 | ishit | Content | Homepage hero + CTA copy | Not Started | Conversion | aaradhya implements
W1 | ishit | Content | Pricing page messaging | Not Started | Conversion | aaradhya implements
W1 | ishit | Content | Draft 3 blogs (copy trading, MT5, AI coach) | Not Started | Organic | aaradhya helps publish if CMS/code
W1 | ishit | Content | 12-post social calendar | Not Started | Awareness | None
W2 | abhishek kushwaha | Growth | Launch Discord/Telegram | Not Started | Community | aaradhya wires site links
W2 | abhishek kushwaha | Growth | Recruit 5 traders for MetaAPI testing | Not Started | UAT help | sunish runs sessions
W2 | abhishek kushwaha | Growth | Weekly growth report #1 | Not Started | Visibility | aaradhya PostHog access
W2 | ishit | Content | Publish 3 blogs | Not Started | Organic | SEO meta by aaradhya
W2 | ishit | Content | MT5 connect guide + welcome emails | Not Started | Activation | Email send config if needed
W2 | ishit | Content | 1 product Short/Reel | Not Started | Awareness | None
W3 | abhishek kushwaha | Growth | Invite campaign for first 20 beta users | Not Started | Activated users | abhishek allowlist
W3 | ishit | Content | Risk guide + testimonials | Not Started | Trust | None
W4 | abhishek kushwaha | Growth | Expand to 50 + referral messaging | Not Started | Growth | None
W4 | ishit | Content | 3 Shorts: dashboard, coach, MT5 | Not Started | Views | None
Ongoing | abhishek kushwaha | Cadence | 2h outreach · 2h campaigns · 1h community · 1h competitor · 1h reporting · 1h coord | Not Started | Acquisition | None
Ongoing | ishit | Cadence | 3h writing · 2h social · 1h website copy · 1h FAQ/brand | Not Started | Content engine | Hands copy to aaradhya

## Website Checklist (1)
Page | Exists | Eng Owner | Content Owner | Content Ready | SEO/Code Ready | Prod Live | Priority | Notes
/ | Yes | aaradhya | ishit | Partial | Partial | Partial | Critical | LCP + copy
/pricing | Yes | aaradhya | ishit | Partial | Partial | Partial | Critical
/about | Yes | aaradhya | ishit | Partial | Partial | Partial | Medium
/blog + slugs | Yes | aaradhya | ishit | Not Started | Partial | Partial | Critical
/guides + slugs | Yes | aaradhya | ishit | Not Started | Partial | Partial | High
/brokers + slugs | Yes | aaradhya | ishit | Partial | Partial | Partial | High
/login /register /verify | Yes | aaradhya | — | Yes | Partial | Blocked | Critical | OTP = sunish
/onboarding | Yes | aaradhya | ishit | Partial | Partial | Partial | High
/dashboard + trading UI | Yes | aaradhya | ishit | Partial | N/A | Partial | Critical | Backend = sunish
/billing /wallet | Yes | aaradhya | abhishek kushwaha | Partial | N/A | Blocked | Critical | Payments = sunish
/alpha-coach | Yes | aaradhya | ishit | Partial | N/A | Partial | High | Coach API = sunish
/help /docs | Yes | aaradhya | ishit | Partial | Partial | Partial | High
/legal pages | Yes | aaradhya | abhishek | Yes | Yes | Partial | High | Sign-off
/status | Yes | aaradhya | — | Yes | Yes | Blocked | Critical
/contact /community /press | Yes | aaradhya | ishit | Partial | Partial | Partial | Medium
sitemap/robots | Yes | aaradhya | — | Yes | Partial | Partial | Critical